## Slide 1: Session 11
Indicators (II)
Sources of verification

## Slide 2: Indicators – Different types of measures
Cardinal measure: a number of absolute units (relative, cumulative…) e.g. number of people trained during the project
Ordinal measure: a non numerical ranking measure e.g. level of satisfaction of users
A binary measure: go/no go e.g. existence of a law
A signal: element confirming the respect of deadline e.g. one workshop per quarter during the year Y
A calculation: a ratio, a rate, a trend e.g. a fecundity index
Simple or complex quantitative indicators, indexes, proxies, …
See practical guide for IFAD Monitoring & evaluation, table 5-7 pg 22 chap 5

## Slide 3
Elementary indicators: basic information from which more complex indicators can be derived
Derived indicators: ratio or rate, from the relationship between two elementary indicators
Compound indicators: combination of several indicators (elementary or derived)
Indicators – different levels of complexity

## Slide 4: Sources of verification
Cost
Complexity
Administrative
records
Management
reports
Existing
statistics
Adapted / processed
statistics
Project funded
surveys
The diversity of sources is reflected in their cost and complexity…
Administrative records, Routine statistics, Management reports, Site inspections, Technical reports…
The source of verification should be explicit! A line Ministry is not a source of verification, it is rather the survey conducted by a given Directorate/Unit within this Ministry…
Notes: 20

## Slide 5: Data Sources
List the specific data sources (do not just list the organisation, mention also the specific data collection method e.g. survey or report)
Frequency should be clear and consistent with milestones and targets
Provide disaggregated data as required
Data collection and reporting responsibilities are clearly specified
In your LFM avoid « project report » in the source of verification column !

## Slide 6: What makes a good data source
Existing – e.g. DHS (demography and health surveys), MIS (malaria indicator survey)
Relevant – meets our needs
Valid – accurate methods used
Reliable – stable & consistent data collection methods used over time
Available – agreed responsibility for data collection, e.g. implementers/ partners
Timely – periodicity consistent with milestones and targets

## Slide 7
« At the end of the 5th year of implementation, 50% of the households in the project area cover 25% of their annual monetary needs through selling services that use skills acquired thanks to training sessions delivered by the project ».
What are the elementary indicators that are required for monitoring information linked to this objective? What are the sources likely to be used for this kind of data? How manageable do you think this will be for monitoring results?
Exercise in pairs| Results, indicators
and sources of verification
Exaemple from du guide pratique de S&E des projets, FIDA
Activity – 5 min. by yourself followed by a plenary discussion
exercicse

## Slide 8: Exercise on objectives, indicators & sources of verification
Take a card and write down a result (output, outcome or impact). Pass to your colleague on the left.
On the card you received from your neighbour, write down an indicator you think could be used to measure this result. Pass to your colleague on the left.
On the card you received write down a source of verification you think could be used to collect the information related to this result and indicator. Pass to your colleague on the left.
Read the objectives, indicator and proposed source of verification you have received and decide if you agree with the choices made.
exercicse