## Slide 1: Session 16
Recap, conclusions & evaluation

## Slide 2: Recap : structure of the training course
Day 1: The logical framework approach
  LFA & the management cycle of development actions
  Thinking outside the box to link context-change-results
  LFA = IL + LFM
Day 2: Intervention logic and the logframe matrix
  Intervention logic
  Logframe matrix
  Exercises & case study

## Slide 3: Recap : structure of the training course
Day 3: Indicators
  The logframe matrix as a living tool
  Indicators & objectives; baselines, targets & milestones
  Sources of verification & critical analysis of data
Day 4: Results measurement, the LFA during implementation
  Monitoring systems and result oriented management
  Case study: structuring indicators in a logframe matrix
  Recap, conclusion & evaluation

## Slide 4
Key messages

## Slide 5: Key message – Overall approach
A development action should lead to change
Most of the time, a partner’s strategy is our starting point
Context and stakeholders must be understood to ensure a good design and adequate management of an action
Assess stakeholder capacity and capacity development to link the action to an endogenous process of change
Think outside the box to identify the expected change and results.
At DEVCO, LFA = IL + LFM

## Slide 6: Key message – The Intervention Logic
Rigorous thinking before rigorous design
IL is both a process and a product
A facilitated process with key persons saves time later in the lifecycle of an action
Questioning « why/what/how/by when » over time clarifies your intervention logic
Key words: change - stakeholders – engagement - reach
Accountability ceiling: be accountable for and be accountable to manage for

## Slide 7: What is the value added by the Theory of Change to the LFM?
From what we have discussed, what is your view on their:
Similarities?
Differences?
Added value?
…
exercicse
exercicse
See hand out on ToC, ToA and LFM

## Slide 8: Strengths and limitations in the use of the LFM
Share your views and experience of how the LFM is currently used in DEVCO: identify strengths and limitations of the LFM in terms of
The information it provides
Support to project design
Support to project management
Support to project monitoring & evaluation
…
exercicse
exercicse

## Slide 9: Limitations of the LFM
Issues related to the use of the LFM
The LFM is an important tool of the LFA but should certainly not be considered as the only LFA tool, nor as an end in itself.
To produce the LFM, the process is as (if not more) important as the product, so the LFM should not to be a “carved-in-stone product”… a locked frame!
A LFM has to be a living tool. Used as a box ticking exercise, it can prevent the good design and management of actions.
Issues related to the conceptual nature of the LFM
The many intermediary steps between an action and the resulting change are usually not stated in the LFM but need to be understood and monitored
The LFM is a simplified representation of an action, it does not picture the actual complexity of the context nor alternative pathways of change
A tool is rarely bad in itself. It is about when, what for and how it is being used…

## Slide 10: Key message - Logframe Matrix
Dynamic and flexible tool! Context-related so evolving over time
Impact/overall objectives: the relative importance of an intervention within a sector
Outcome/Specific objective: a realistic ambition
Coherence between activities – outputs - outcome: are the keys for the success of the change process present?
Assumptions: be aware of assumptions underpinning steps in the change process and the evidence supporting them
Indicators and sources of verification: coherence with a result oriented M&E system

## Slide 11: Key message - Indicators
Managing for development results & monitoring sytems: start from the beginning
A little technicality and a lot of common sense: KISS for efficient use of indicators
Coherence between objectives – indicators – baseline – targets –milestones - sources of verification
Judgement is never replaced by data. Data inform judgement: keep thinking !

## Slide 12
Step by step into DEVCO’s LFA

## Slide 13: Step by step into the LFA 1/3
What does the AD "formally" request?
  The Logical Framework Matrix for project modality (or the indicative list of result indicators for Budget Support)
  The Intervention Logic summarized by a short narrative
What is the nature of the IL and the LFM?
  IL = thinking process which is sometimes supported/accompanied/described by a diagram and a narrative (it is therefore the summary of this narrative that is requested)
  LFM = management and monitoring tool

## Slide 14: Step by step into the LFA 2/3
How important are the IL and the LFM?
  The IL is essential to ensure critical /strategic thinking leading to context sensitive and evidence based actions: if correctly done, the IL will reinforce appropriation by the main stakeholders of the action. The IL will also be needed to manage, adapt (if necessary) and evaluate the action.
  The LFM is instrumental for the management of an action because it facilitates articulated activity planning and can be used as a common reference among stakeholders. The LFM is crucial to ensure monitoring/reporting on results, supporting management and evaluations thereby fulfilling obligations vis-à-vis the EU institutions (implementing regulations) and commitments at corporate level (EURF).

## Slide 15: Step by step into the LFA 3/3
How to proceed?
  For the IL:
    The IL is conceived as a theory of change from the start
    or
    The IL is first developed trough a method of problem tree/objective tree and afterwards it is revised/checked against a theory of change (through a "backward thinking process": showing how the change will emanate from the outcomes, and these from the outputs and these from main activities)
  For the LFM, depending on the method selected in the previous point, it will be either an output of the theory of change or of the problem tree/objective tree process.
often better added value in terms of quality of IL obtained
easier for starting to work with IL when used to “old LFM-LFA” way of working

## Slide 16: Questions & answers session
exercicse

## Slide 17: Action oriented conclusion of the training course
Sharing & plenary debriefing
To what extent and how do you relate this training course to your work (design process, action document, QSG process, monitoring and evaluation process, dialogue with partners…)
exercicse

## Slide 18: POST-TRAINING TEST & EVALUATION
exercicse