Amended work plan of the project

Improve the livelihoods of urban and rural poor women dependent on informal sector in Egypt

| Activity | 1st year |  |  |  |  |  |  |  |  |  |  |  | The implementing body |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Month 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |
| MOSS approval |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Identify /recruit staff of the main program(CEOSS) |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Training for CEOSS staff |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Prepare for the community surveys |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Recruit the specialized consultants/develop TOR, sign contracts |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| recruitment and training of surveyors |  |  |  |  |  |  |  |  |  |  |  |  | Specialized consultants(under CEOSS follow up) |
| surveys conducted |  |  |  |  |  |  |  |  |  |  |  |  | Specialized consultants(under CEOSS follow up) |
| Results analyzed and database created |  |  |  |  |  |  |  |  |  |  |  |  | Specialized consultants(under CEOSS follow up) |
| Specify the 30 CBOs awarding the sub grants and sign the agreements |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| establish resource centers |  |  |  |  |  |  |  |  |  |  |  |  | The sub grantees (under CEOSS follow up) |
| Train the CBOs staff |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Community raising awareness meetings |  |  |  |  |  |  |  |  |  |  |  |  | CEOSS |
| Receive progress reports every quarter |  |  |  |  |  |  |  |  |  |  |  |  |  |

| For the following years: |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Half year 3 | Half year 4 | Half year 5 | Half year 6 | Half year 7 | Half year 8 | The implementing body |
| Train women |  |  |  |  |  |  | The resource centers and the specialized training (under CEOSS supervision) |
| Technical support and reaching fund |  |  |  |  |  |  | The resource centers (under CEOSS supervision) |
| Form the committees and the capacity building groups |  |  |  |  |  |  | CEOSS and the CBOs |
| Train on the advocacy and its activities |  |  |  |  |  |  | CEOSS ,Specialized consultants |
| Knowledge production and the network activities. |  |  |  |  |  |  | CEOSS ,Specialized consultants |
| Follow up reports |  |  |  |  |  |  | CEOSS |
| Monitoring and evaluation |  |  |  |  |  |  | CEOSS ,specialized consultants |
| Develop TOR and sign the contract with the evaluator |  |  |  |  |  |  |  |
| Finish the monitoring and evaluation plan (baseline data defined ,indicators defied ,data gathering ,schedule set ,data gathering instruments developed ) |  |  |  |  |  |  |  |
| The evaluation reports |  |  |  |  |  |  |  |