| EUROPEAN EXTERNAL ACTION SERVICE |  |
| --- | --- |
| EUROPEAN EXTERNAL ACTION SERVICE | MD VI Global and Multilateral Issues The Managing Director |

EEAS.VI.A3/SD/1760148

Guidance Note on the Second Generation of countries for
Pilot Work on Democracy Support

for the EU Delegations IN

Georgia, Republic of Moldova, Fiji, Malawi, Mozambique, Tanzania, TunisiA, Morocco, timor Leste, Myanmar/Burma, PAraguay and Nepal.

PART I – THE "WHY"

Introduction

1. This is a guidance note to Delegations prepared by EEAS in agreement with DEVCO for the work to be done on the second-generation of pilot countries for democracy support. This exercise stems from the 2009 Council Conclusions on Democracy Support in the EU’s External Relations which state that one of the objectives of EU’s external actions is to develop and consolidate democracy, rule of law and respect for human rights in a coherent and effective manner.

2. The EU's commitment to work on democracy in third countries was included in the EU Strategic Framework and Action Plan on Human Rights and Democracy adopted by the Foreign Affairs Council in June 2012. The Agenda for Change from October 2011 also highlights the importance of democracy and states that the EU should concentrate its development cooperation in support of human rights, democracy and good governance as well as inclusive and sustainable growth. A decision was taken to test a new approach to democracy in a number of pilot Delegations. A first pilot exercise was conducted in 9 countries in the years 2011-2013. We are now launching a second-generation of pilots for democracy support based on chapter III.6.b of the Action Plan.  According to PSC decision of 4 March 2014 the exercise will be carried out in Georgia, Republic of Moldova, Tunisia, Morocco, Malawi, Mozambique, Tanzania, Fiji, Timor Leste, Burma/Myanmar, Paraguay and possibly Nepal.

Mandate

3. The EU is mandated to work on democracy based on the Treaty Article 21:1:

"The Union's action on the international scene shall be guided by the principles which have inspired its own creation, development and enlargement, and which it seeks to advance in the wider world: democracy, the rule of law, the universality and indivisibility on human rights and fundamental freedoms."

Rationale

4. The main purpose of this exercise is to increase coherence to achieve better impact of the EU's work in the field of democracy. It provides an opportunity for the EU to try new ways of working on democracy and, where possible, an opportunity for the partner countries to share what they consider works best for them.

Benefits

5. The value-added is:

- a strategic look at all aspects of our relations with third countries having bearing on democratisation, and

- identification of actions to increase coherence of EU action by:

- new working methods,

- better programming and stronger linkages between on-going activities, and

- better use of funding from EU instruments and other donors;

6. This action will require a strong collaboration between colleagues from political and operational sections of the Delegations, as well as close work with Member States.

7. Each Delegation's contribution will help shape the policy of the EU when it comes to democratisation. The Delegations will thus take the ownership of the ongoing work on democracy and will lead on the practical implementation of this exercise.

8. Through this exercise we have the ambition to strengthen our patterns of work into a more holistic and comprehensive approach to democracy support. In addition to delivering technical assistance to build the country's competences and capacities we aim to address the underlying political weaknesses that impede democratic reforms of the country. Among the expected outcomes are products that can later be developed for global use as well as ideas on across-the-board approaches to democracy work.

PART II  - THE "WHAT" - CONTENT

Expected deliverables from Delegations

9. Delegations are expected to deliver two documents:

- a "Democracy Profile" and

- a "Democracy Action Plan".

Both of them should be validated by HoMs.

10. We will also ask you for a feedback with your experiences from this exercise (see point 16).

11. We may offer you a template based of the best DP and DAP prepared in the first pilot exercise as an example of what you may wish to use.

Democracy Profile (DP)

12. A Democracy Profile is an analysis of the state of democracy in a country concerned. It has to:

- describe the set-up of institutions which together comprise the formal aspects of a democracy; and

- provide an analytical link to the outcomes of the democratic system (fulfilment of economic and social rights and more equitable redistribution of wealth, efficient use of public resources, anti-corruption work, gender equality, quality of the rule of law, security sector reform, more inclusive political environment - to name a few of them).

13. A non-exhaustive list of issues that you can tackle in your analysis could cover inter alia the constitution, the electoral system, the division of power, the democratic role of political parties, the powers and capacity of the parliament, accountability to voters, etc.

13.a. The basis for the political system in many countries is a constitution. Democratic transitions and consolidation processes often require constitutional reform. The constitution can redefine the nature of government, its relationship with citizens and the nation's vision and identity. It plays a fundamental role in the division of power in the public sphere. It also can (or not) include (or exclude) protection for the rights of identifiable groups based on sex, race, colour, caste, ethnic or social origin, language, religion or belief, political or any other opinion, membership of a national minority, disability or sexual orientation. It often contains a bill of rights. It is important to keep in mind that democratic constitutions have both a content aspect and a participatory process aspect. The perfect content will not suffice if there is no buy-in of key stakeholders.

13.b. The role of elections is to recognise the individual voters as the basis of the political system. Their views need to be aggregated, usually through political parties. The choice of electoral system has profound effects on political life in a country, as does the quality of the functioning of political parties. We need to develop a much deeper understanding for the interplay between the choice of a system and actual political outcomes, including levels of conflict as consequence of choice of system.

13.c. Solid political parties and in consequence multiparty parliaments are indispensable actors in democratic political systems. They are also, in general and across the globe, some of the weakest actors in the democratic systems. Ideas on how to strengthen the parties' abilities to represent voters and to take on board their concerns by proposing legislation through proper parliamentary procedures would be an important consideration for this pilot exercise.

13.d. Accountability of elected officials towards citizens throughout the whole election cycle should be a part of the analysis. On this topic, it is crucial to analyse the possibility for CSOs to act both as implementing partners and watchdogs of the actions of elected officials. General freedom of expression as well as capacity of the media to report freely and independently must also be assessed.

13.e. Some attention needs to be paid to the division of power arrangements and how well they function; besides the obvious between legislative, executive and judicial powers, also horizontal divisions such as decentralisation, local authorities, etc. Please study a distinction between formal set-up and informal arrangements (e.g. clientelism or patronage shaping selection of candidates for political posts, etc.).

Democracy Action Plan (DAP)

14. Building on your Democracy Profile analysis, a Democracy Action Plan needs to:

- identify priorities in a democratisation process of the country,

- link them with available tools,

- determine new working methods for the EU.

The added-value of a Democracy Action Plan is to demonstrate the coherence between the political dialogue and other EU foreign policy instruments and development and financial cooperation as well as between the work done by the EU and its MS.

15. While drafting a DAP please choose democracy priorities that could optimally become realistic results of our actions. Bear in mind that you need to identify necessary financial resources and instruments for their realisation, but you may also identify priorities/actions that do not require funds but new ways of working (for example regular exchanges on advancing democracy between the heads of political and operational sections of the Delegation or closer contacts by the Delegation with lower ranking staff from the national parliament, such as those individuals who participated in exchange programmes with the EP or with parliaments of MS).

Your feedback

16. The Democracy and Electoral Observation Unit in the EEAS would appreciate your remarks (in the format that you would find best) with your feedback on methods, opportunities and challenges you have encountered in the process of preparation and implementation of DP and DAP. This will provide the input for the HQ reporting to the Council on the development of democracy support work. Ideally we need to present to the Council concrete examples on how to work at a country level, keeping actual results/impact as focus and preferably engaging both partner government and civil society. Your experience from the field is invaluable in assessing the EU's impact and for drawing lessons that could be relevant for other countries.

Deadlines

17. A Democracy Profile is expected no later than 1 December 2014 and a Democracy Action Plan is expected by 1 March 2015. Both of them need to be developed with MS and validated by HoMs. In case of a specific and objective reason to move those deadlines the Head of Delegation should present the justification to the HQ asap. The feedback with your experiences is expected just after you deliver the DAP.

18. Overall reporting of the work on democracy support to the Council will be done in the Annual Report on Human Rights and Democracy. Implementation of the Democracy Action Plan and evaluation of the work (together with the partner country, preferably) should continue through 2015 into 2016/2017.

19. This is a long-term exercise and the deadlines indicate that we value quality and an ambitious approach over speedy results. The validity of your DP and DAP will be for the period 2014-2017.

| When? | What? | To whom? |
| --- | --- | --- |
| 1 December 2014 | Democracy Profile | Validation by HoMS and delivery from Deleg to HQ |
| January 2015 | Overall reporting on democracy part of Annual Report on Human Rights and Democracy | HQ to Council and EP |
| 1 March 2015 | Democracy Action Plan | Validation by HoMs and delivery from Deleg to HQ |
| June 2015 | Your feedback on challenges and successes | Deleg to HQ |
| Throughout 2015 and 2016 | Implementation of a Democracy Action Plan | Deleg and MS |
| January 2016 | Overall reporting on democracy part of Annual Report on Human Rights and Democracy | HQ to Council and EP |
| November 2016 | Evaluation and Report on implementation of Democracy Action Plan | Deleg and MS and where possible partner country – information to HQ |
| January 2017 | Overall reporting on democracy part of Annual Report for Human Rights and Democracy | HQ to Council and EP |

What democracy? Strong link with human rights

20. Our approach to democracy needs to mirror our work on human rights. For the EU all human rights are universal, interrelated and mutually supportive. Democracy is the only political system in which – through proper mechanisms – people can claim and realise their civil, political, social, economic and cultural rights. Our conceptualisation of democracy needs to reflect this. At the core of a traditional approach are the elections. A liberal approach embraces civil and political rights – but without a political system that also delivers on economic, social and cultural rights, there is no full democracy. The analysis in Democracy Profiles needs to recognise this and most of the EU and MS engagement in development also reflects this understanding.

21. The issue of a definition of democracy was debated in the Council in 2009. The conclusion was that the lack of a precise definition of democracy which EU supports may be an advantage as it allows for flexibility and adaptation to the context of the country concerned. It seems wise to avoid promoting specific institutional solutions and use the 28 European MS as variations on how to address institutional needs while reflecting basic democratic principles.

22. Bearing in mind the multiplicity of models of democracy, what they all have in common is that "democracy" provides space for disagreement without resort to violence. At the core of the EU's defence of democracy is the acceptance of differences of opinions and political contestation, openness for dialogue and the accountability to the citizens.

23. Democracy is therefore the broadest concept - the umbrella that encompasses our work on human rights, elections, civil society, good governance, gender and rule of law. Only when all of these elements are in place we may talk about real democracy – having for example technically perfect democratic elections is not enough if there is no freedom of expression or free media which enable society to hold governments accountable after elections.  A development of a democratic culture is therefore essential as it would give us the possibility of supporting democracy from different angles.

24. Respecting the local context we should acknowledge that in some cases a "European approach" to democracy might have its limitations. While maintaining a commitment to universal values, we should be able to accept alternative institutional solutions keeping however the outcome in mind (full realisation of human rights).

Principles on which EU's democracy support is based

25. The 2009 Council Conclusions (doc. 16081/09) include the EU Agenda for Action which  specifies that democracy support needs to be based on the following principles:

A. Country-specific approach

26. Tailor the activities under the pilot exercise to the country's context and to the opportunities that arise during the period of work. Focus on areas that you think are best suited to tackle democracy deficiencies. Some examples of issues you might address are: challenges to liberation movements that have turned into political parties, special features of presidential systems, sectarian politics, lack of civilian control over natural resources, particular issues related to gender, or civilian control over armed forces to name a few. The approach to democracy issues and to this exercise might be different depending on the context of the country.

B. Dialogue and partnership

27. Pursuing democracy support through dialogue and consultation with local partners enhances domestic ownership of democracy building processes. The ideal scenario would be to involve in preparation of the DAP the authorities of a partner country as well as other key players in the democratic set-up: civil society, political parties, media, academia, trade unions and other relevant players. The partnerships that the EU promotes are tripartite dialogues between the EU, the government and civil society at one table. Pay attention to who is included – and excluded – in the CSOs. The choice of partners will greatly influence the outcome (for more on partnership see points 42-45).

C. EU coherence and coordination

28. A closer coordination between the EU's foreign policy instruments and development cooperation will be a necessary starting point for applying a holistic approach to democratisation of a third country. Coordination is needed both at HQ and at the Delegations' level and it should start from country analysis stage through planning to implementing democracy priorities.

29. At HQ level the EEAS and DEVCO geographical desks cooperate on this exercise with an involvement from horizontal desks. At the Council this exercise was prepared jointly by COHOM and CODEV working groups. The geographical groups will be kept informed about the process and the DPs and DAPs will also be presented to them for information.

30. Part of the EU coherence, but a layer outside the institutions, is the work done by EU Member States. The Joint Programming already launched in a number of countries could be a vehicle to ensure better division of labour that can use best the value-added of different EU Member States experiences, culture and language.

D. Mainstreaming

31. Support for democracy demands consistency and linkages through all EU actions. The case for mainstreaming is most obvious in the focus sectors for development cooperation. Where possible delegations are encouraged to go one step further by applying recently adopted toolbox on rights based approach to development. The examples of such actions should be included in the DAP.

E. International cooperation

32. Democracy support can be used as a topic of collaboration between the EU and other international actors present locally, such as the UN, regional organisations and/or other countries. Your DP and DAP will feed into dialogue on democracy's meaning with other partners at international fora. Debating democracy with your partners on the ground may be a very good way of defending democratic ideals and learning about demands/interpretations of democrats from different parts of the world.

F. Visibility

33. There are demands for more visibility of EU's actions on democracy and human rights. While visibility can not be an aim in itself, giving more transparency and visibility to our actions may, in some cases, increase the impact of EU democracy support.

34. Choose the level of visibility deemed most fruitful for the successful implementation of the pilot exercise. In cases where putting democracy on the agenda of a political dialogue is an option and where it may be discussed in a tripartite format, visibility of the process is desired.

35. None of the first generation pilot countries produced information or work on international cooperation and/or visibility. Please share your views on how to advance this principle.

PART III – THE "HOW" - PROCESS

Existing resources as building blocks for DP and DAP

36. Delegations are already engaged in several processes covering democracy-related substance so there is of course no need to start from scratch. You should build on the work already done and use it to create synergies and identify optimal activities for supporting democratic transitions or consolidating democracy in your countries.

37. Your analysis in a Democracy Profile should be based on and be consistent with the assessment of certain aspects of democracy in the following existing sources:

- human rights country strategies;

- reports from EU, OSCE/ODHIR, domestic and other Election observation missions and Follow-up missions;

- ENP progress reports;

- roadmaps for engagement with civil society;

- assessments of fundamental values for Good Governance and Development Contracts;

- risk management frameworks for budget support;

- early warning and conflict prevention analysis;

- as well as political reports from your Delegation.

38. Then democracy related priorities from the human rights country strategies, ENP action plans, civil society roadmaps, budget support contracts, recommendations from EOMs should feed into the DAP. You are asked to look at them in a strategic, holistic way and prioritise them in the DAP.  After identifying your democracy priorities you are required to determine needed actions. Then you have to, where relevant, refer to funding from different EU financial instruments (geographic and thematic), and specific projects/programmes, especially those directly linked to democracy support (eg. Good Governance and Development Contracts, electoral assistance or projects on democracy as focal sector for ENI/DCI/EDF). As already indicated, refer also to resources eg. from MS or other donors. This exercise should be linked with programming and preparation of implementation of the EU instruments and also, to the extent possible, with the Joint Programming with MS.

39. Taking into consideration the already advanced status of the bilateral and regional programming under geographic and thematic instruments, and the focal sectors already identified, please align preparation the DAP with your work on Annual Action Programs under the relevant instruments. Your work on the DAP should also help structure Mid-Term review of the programming. Reflect whether your programmed actions will tackle democracy deficits in the country and assess how you may use the rights based approach to development to design projects/programmes from current programming that can contribute to consolidation of democracy or to stimulation of a democratic transition in the country.

Suggested first steps

40. As a starting point it is advisable to organise a serious brainstorming on how to put together the elements related to democracy in all aforementioned processes and portfolios of the EEAS and DEVCO staff. Discuss among the Delegation staff what are the most serious democracy deficiencies in the country and what priorities the EU should choose to address them.

41. Then invite MS to join in.  One of the purposes of this exercise is the improvement of the work on democracy issues between EU institutions and Members States by better joint programming. Ask MS present on the ground to contribute to the analysis in DP and to share information about democracy projects they are funding so that they can be included in the DAP. As mentioned above, the DAP needs to be validated by HOMs. A non-paper outlining the process was circulated in Brussels to MS via COHOM and MS were asked to brief their embassies in those 11 countries and to encourage them to participate in this exercise.

42. Following the principle of partnership and ownership it is desirable to conduct this exercise with your partner country to deepen our understanding of what works best for them. The Head of Delegation shall determine how to approach the authorities and what would be the best format to work with them on the DAP priorities and gaps in the EU actions.

43. Do not invite the partner to "be a pilot" - experience from the first pilot exercise showed us that this wording remains internal to the EU institutions, as it can be perceived as rather patronising. It is the EU itself that is piloting new working methods to improve its ability to understand better the country. The EU's message in introducing this work should be along the following lines: The EU is willing to learn what works best in your country and we wish to improve our performance based on your reflections.

44. The level of the engagement of the government in preparing the DAP depends on your judgement. In some countries you may be able to elaborate together priorities for the DAP; in others you may only have more general discussion with the government and more substantial work with non-governmental partners. In the first pilot in case of Bolivia, democracy support was added to the High-Level Dialogue between the EEAS (MD) and the country (foreign minister) and a joint working group was created between the Delegation and the MFA. Adding democracy support as a topic to the political dialogue is a useful model that is encouraged. The other possibility is an expansion of the agenda of human rights dialogues to broader democracy issues.

Talking points to the government of the pilot country

45. In your communication with the government we suggest to underline that:

- The EU chose for this exercise countries that already demonstrate a positive engagement toward democracy and human rights;

- The EU wishes to recognise the country's efforts and contribute to steering further progress in the democratic transition.

- The EU is willing to learn what works best in your country and we wish to improve our performance based on your reflections.

How were countries selected?

46. Countries were chosen on the basis of criteria agreed by COHOM and CODEV in March 2013. The criteria were:

- willingness of the country to cooperate and improve;

- countries that are important recipients of EU aid also through budget support;

- usefulness of lessons from your country for other countries;

- recent or planned elections;

- EOM or EEM in the country;

- constitutional reforms and

- capacity in the Delegation.

Please use your assessment of the ongoing or recent elections or constitutional reviews in preparation of both a DP and a DAP.

47. Use the cycle approach: - map the democracy landscape: who are the key players, in-country and among donors and other international actors; - draft the Democracy Profile to assess strengths and weaknesses in key institutions and the processes they engage in; - use the mapping and the DP to identify clear key priorities for democracy in your country; - consult with partners on their views and agree on a Democracy Action Plan; - implement the Plan ;- identify lessons learned; - evaluate it – and, if appropriate, launch another cycle.

48. Who takes the lead in the Delegation for this exercise is a matter for a local decision, bearing in mind that the Council Conclusions requested for increased coherence. The focal point for human rights should be involved but it is up to the HoD to decide who in your delegation would be best suited to collate democracy elements across the portfolios of different staff.

Confidentiality

49. The first pilot exercise brought up the issue of the level of confidentiality. The conclusions for the second pilot is that you need to strike a proper balance between transparency in preparation of a DP and DAP and the political objective of achieving greater impact.  It is up to you to decide whether you would prepare together and share a DP and DAP with the government, or you just provide them with resume of a DP and DAP (or only DAP) or you produce most of the work in the form of internal EU documents.

Be creative

50. A pilot project is a learning exercise for all of us. Your creativity, fresh viewpoints, unconventional and out-of-the box approach to democratisation and testing new working methods is most welcome. Please do not feel restricted by what you can find in a template and feel free to adapt it to your needs and ideas.

Resources

51. This project is not about allocating new resources but is primarily about the principles identified in the Council Conclusions towards increased coherence, streamlining, better programming and use of EU funding from different EU instruments and donors towards more impact as regards democratisation. There are therefore no additional financial resources earmarked for this work, however in some cases delegations may ask to use the "support measures" part of EIDHR CBSS (10% of the EIDHR CBSS country allocation) to help implement the pilot exercise, for instance for commissioning gap analysis or organising multi-stakeholders workshops. In addition, DEVCO.B.1 will shortly issue a tender which has a goal inter alia to support the active involvement of local CSOs in the preparation of the DPs and DAPs.

52. Apart from the Council Conclusions and a Strategic Framework relevant policy documents include: Communication "Increasing the impact of EU Development Policy: an Agenda for Change", Communication "A new response to a changing Neighbourhood" (COM 2011/303),  Communication "Neighbourhood at the crossroads – taking stock of a year of challenges" (JOIN 2014/12), (COM 2011/637), Communication "The roots of democracy and sustainable development: Europe's engagement with Civil Society in external relations" (14535/12), Communication "Empowering local authorities in partner countries for enhanced governance and more effective development outcomes" (COM 2013/280), Communication "The future approach to EU budget support to third countries" (COM 2011/638). The relevant legal framework includes: Regulation 233/2014 establishing a financing instrument for development cooperation for the period 2014-2020, Regulation 235/2014 establishing a financing instrument for democracy and human rights worldwide, Regulation 232/2014 establishing a European Neighbourhood Instrument, Regulation 230/2014 establishing an instrument contributing to stability and peace, Regulation 234/2014 establishing a Partnership Instrument for cooperation with third countries, Regulation on the implementation of the 11th European Development Fund COM(2013) 445 and future Internal Agreement on EDF.

53. DEVCO has commissioned several practical guides on key work areas: elections, parliamentary support, media and support to political parties (all are available at www.eidhr.eu website). There is also work on-going on political economy analysis (PEA), highlighting the importance of quality in political decision-making from the economic perspective, potentially very important in this process.

54. Here are some examples of external resources:

- On overall democracy assessments:  www.VDem.net; www.idea.int/sod

- On constitution-building processes:  http://www.constitutionnet.org/knowledge-tools

- On electoral systems: www.idea.int/esd; www.ifes.com; http://aceproject.org/epic-en;  http://aceproject.org/epic-en;http://aceproject.org/electoral-advice/dop/recommendations;

http://www.idea.int/elections;http://www.idea.int/elections/ermtool/index.cfm; http://idea.int/uid/index.cfm

- On political parties: http://www.idea.int/publications/strategic-planning-for-political-parties/index.cfm and http://www.idea.int/publications/political-party-dialogue/index.cfm; www.idea.int/parties; www.nimd.nl

- On realisation of social and economic rights (=outcomes of the democratic system): the Human Development Index by UNDP

- On anti-corruption work: Transparency International

- On practical examples of actions of diplomats on democracy issues – A diplomat's handbook for Democracy Development Support (Diplomat's Handbook | For Democracy Development Support.)

55. We count on your cooperation to successfully deliver results from this pilot exercise. Please send information who at your Delegation will be in charge of this exercise to ingrid.wetterqvist@eeas.europa.eu and sylwia.domisiewicz@eeas.europa.eu.  For any questions please contact your geographical desk in HQ or Ingrid Wetterqvist (tel: 0032 2 584 94 17) or Sylwia Domisiewicz (tel: 0032 2 584 2030) in the EEAS Democracy and Electoral Observation Division.

A concept of "deep democracy" – that could serve as an example of a definition - was introduced in a Joint Communication from May 2011 entitled "A new response to a changing Neighbourhood".   It underlined that in order to build deep and sustainable democracy the country requires: - genuine, democratic elections; - freedom of association, expression and assembly and a free press and media; - the rule of law administered by an independent judiciary and right to fair trail; - fight against corruption and security and law enforcement sector reform and the establishment of democratic control over armed and security forces.