|  | EUROPEAN COMMISSION Directorate-General for International Cooperation and Development Operational Information Systems |
| --- | --- |

Opsys – New operational information system for DEVCO, NEAR, FPI

Status for the 12 December 2016 IT Board meeting

References:

- ARES(2016)2668822, note DEVCO sent on 8 June 2016

- ARES(2016)3211364, operational conclusions of the 9th IT Board meeting

The IT Board has invited DEVCO in its 22 June 2016 meeting to report back in November 2016 on:

- A detailed work plan for Project 2B for all involved parties

- A proposal for a local governance set up

- A solution for the sharing of costs

- An approach on the JaGate interface

Summary: The preparation of the re-use of corporate solutions for Opsys project 2B has been intense since June while market by a turn over from DEVCO and DIGIT side. Key milestones have been agreed for the work plan and particularly with the testing of a pilot on SIGMA in Q4 2017. A partnership agreement between DEVCO, NEAR, FPI, DIGIT and RTD has been drafted with a local governance set up built on the existing Opsys governance. A proposal is made by DIGIT and DEVCO regarding the sharing of costs for the part of the re-use serving corporate needs. And a joint approach between RTD, DEVCO and DIGIT is proposed for the evolution of the JaGate interface. Finally it is worth to note that all proposals made are subject to final approval by the DEVCO IT SC enlarged to DG NEAR and FPI, and planned on 30/11/2016.

Details:

The present note provides a state of play on Opsys on those four points in line with DG DEVCO note sent on 8 June 2016 ARES(2016)2668822. Opsys is work in progress and the preparation for the implementation of the re-use of corporate solutions for Opsys project 2B “contract management” and related IT components has passed important milestones while for others the completion is close.

Two important events are planned by the end of the year with the next DEVCO IT Steering Committee on 30/11/2016 and with the signature by DEVCO, NEAR, FPI, DIGIT and RTD of a partnership agreement which are called to endorse the technical re-use solution and the way to work together.

- A detailed work plan for Project 2B for all involved parties:

The partnership agreement mentioned above will drive the way partners will work together. It is setting the context, rationale, scope, governance, overall budget and responsibilities. It will be completed every year by an annual MoU and work plan defining the next year milestones, activities and related resources.

The scope covers the re-use of corporate solutions and components for Opsys globally and particularly for project 2B "contracts and level 2 commitment".

The detailed work plan for 2017 is under preparation and will follow the signature of the partnership agreement. The work plan is expected by mid-December 2016.

The key milestone for 2017 for project 2B will be the production of a pilot on SIGMA. The definition has been done and the choice has been made for the scope: the pilot will cover DEVCO framework contracts currently managed with CRIS. As analysed in the June 2016 CBA (cost benefit analysis) DEVCO framework contracts differ from DIGIT framework contracts and are specific enough to test the feasibility with SIGMA. The pilot is planned to be in test phase in Q4 2017; according to the final implementation planning it might be deployed progressively as of Q1 2018.

A second pilot is planned on grants and should be implemented in 2018. Several steps are planned until Q1 2019 in order to allow the management of other contracts types (procurement, budget support,…) in order to lead to the phase out of CRIS contract.

A budget is being secured for 2017, pending DEVCO IT SC decision, and a cash flow has been established until the completion of project 2B for the total estimate of 10.9 M€ related to the re-use part for the post award phase. Tentatively: 3.0 M€ in 2017, 3.9 M€ in 2018, 3.0M€ in 2019 and 1.0 M€ in 2020.

And finally project documents are being produced for project 2B in accordance with PM2 standards. A specific business case has been drafted and will be submitted for approval to the next DEVCO IT SC.

The departure of the DEVCO business manager for project 2B may delay slightly the delivery of milestones and artefacts. In particular the work planned on the elimination of business needs and harmonisation of processes has been postponed until a replacement is operational.

- A proposal for a local governance set up

The proposal for a local governance set up is part of the partnership agreement which approval process is planned in November 2016. The local governance builds as much as possible on the existing Opsys programme governance in order not to multiply governance bodies: same decision making structure (enlarged DEVCO IT SC), back to back steering committee level.

The proposed structure yet to be endorsed along the partnership agreement is depicted below and based on the following principles:

- It should manage the stakeholder complexity (DEVCO, NEAR, FPI, DIGIT, RTD, BUDG for the interface with ABAC part)

- Decision making level: the proposal is to use the existing enlarged DEVCO IT SC, in order to avoid the multiplication of structures

- Program steering committee level: the proposal is to have the IT/re-use Steering Committee meeting back to back to the Opsys programme steering committee with the possibility to have partiicpants in common. The Opsys programme steering committee remains competent for business related issues and overall Opsys coherence

- Opsys Re-use Project office level: the proposal is to create a Common Opsys Re-use Project Office (CORPO) that will closely coordinate with Opsys Programme Management Office

Partnership Agreement Scope

OPSYS Scope

DEVCO ITSC (extended)

OPSYS Program SC

IT/Reuse SC

OPSYS SC

OPSYS Reuse PO

OPSYS PO

BusinessGroup

Architecture Group

Reused Components Projects

Reused Components Projects

DEVCO Components

DEVCO Components

Non-reused

DEVCO specific Components

Reused Components Projects

- A solution for the sharing of costs

Coming from CBA figures the evaluation of costs linked to a corporate benefits and therefore subject to the sharing of costs is estimated by DEVCO for project 2B re-use (post award phase) to 2.040 M€. Those costs are exclusively linked to the re-use of the post award phase of e-procurement (see details in the table in annex).

In parallel a decision has been taken at the ABM September meeting to mutualise the costs for the deployment of e-procurement between all DGs called to use the system, as for DEVCO, NEAR and FPI, according to a contribution key based on turn over and number of transactions. The share of DEVCO NEAR FPI in that exercise is estimated between 0,5 and 0,6 M€ per year during 4 years, starting in 2017.

DEVCO in agreement with DIGIT suggests to compensate the 2.040 M€ part of project 2B estimate for re-use by a 80% offsetting of what should be recovered for the e-procurement deployment in 2017, 2018, 2019 and 2020. In other words DEVCO NEAR FPI will pay for the identified 2.040 M€ while getting an exemption for 80% of the mandatory contribution to e-procurement deployment for four years (see figures in annex).

Further compensation might be needed for costs linked to corporate benefits as for example if DEVCO/NEAR/FPI engages in the pre-award phase (project 5 of Opsys). In that case ad hoc solution should be found and could be based on the following:

- Either new partners have come on board in between and cost can be mutualised

- Or DEVCO NEAR FPI will front load for the corresponding investment and will get a reduction in term of maintenance costs.

- An approach on the JaGate interface

At the 9th IT Board meeting DG BUDG adopted the following position, supporting the extension of JaGate-ABAC interface to other systems including Opsys:

“With regard to specific building blocks, Ms Gheorghe supported the idea to explore the extension of the use of JaGate-ABAC interface to other systems”.

DEVCO NEAR FPI agreed to re-use JaGate interface provided that the CRIS ABAC rationalisation objectives could be reached in the long term, meaning through the availability of web services (so called data check service). The joint approach proposed by RTD/DIGIT/DEVCO after a first round of discussions with DG BUDG in July and September 2016 as described in annex is as follows:

- DG BUDG agrees that JaGate is a complimentary service to ABAC for which there is no plan to implement such service

- All parties will work together in order to assess the feasibility to deliver web services (data check services) for commitment level 1 in coherence with Opsys project 2A roll out (Q1 2019); a 1 equivalent FTE support is provided to BUDG in order to establish a budget and planning by April 2017

- Migration of JaGate to use SoA of ABAC (some of the services were already migrated but not in production yet); delivery of full web services for commitment level 2 will be planned after Q1 2019 once the detailed analysis of DEVCO transactions and definition of profiles has been made for commitment level 2;

- Simplification of procedures for initial access to web services of ABAC in a non production environment is under discussion with BUDG.

Discussions have taken place with DG BUDG at technical level and a final decision remains to be taken considering the fact that requested web services are not yet part of DG BUDG roadmap.

- Other aspects worth to mention:

The DEVCO IT architecture impact assessment has made significant progress on both functional and application architecture; discussions with DIGIT architecture team have started and final outcomes are expected Q1 2017.

And finally discussions have started between RTD, DEVCO and DIGIT on the convergence of user experience between corporate tools part of the re-use solution and particularly around COMPASS. Timing is an important element for the release planning of Opsys yet to be resolved.

--------------------------------

Annexes:

- Identification of costs subject to cost sharing (costs linked to corporate needs/benefits) and indication of estimated e-procurement deployment costs

- Presentation of the current DEVCO/DIGIT/RTD joint approach on JaGate

Author:

DEVCO 05

Denis Thieulin, ext 61327

Revised 17/11/2016

NEAR and FPI will confirm if they are directly part of the partnership agreement or if they consider that DEVCO will represent them.

The presentation made to the DEVCO IT SC of 08/06/2016 and annexed to the note to the IT Board mentions 11.6 M€ from which 0.7 M€ covers internal DEVCO costs as provision for the issues related to the user interface; other IT DEVCO internal costs are related to migration and integration (estimated at an additional 3.5 M€).