ROMA AWARD 2016-  RELITY CHECK
	Programme 
	ROMA AWARD 2016 

	Applicant No and Title
	Improving Roma Employment  through  education  and Training  KHAM Delcevo 

	Project location
	Delcevo, Skopje  Vinica

	Project Duration
	29/12/2015- 29-12-2017

	Visit date
	26/01/2017

	Persons interviewed 
	Mr Zekir Abdulov, Director and Ms Aneta Conevska, Project manager

	
	Confirm
	Comments and Suggestions

	OPERATIONAL ISSUES

	1
	Grant contractor/s (and their partners) in charge of the management of the project were present in the meeting.
	YES
	Project  Manager and the director 

of the KHAM  were present 

	2
	There is no change in the project action and location.
	YES
	Activities of this project are ongoing.  KHAM is co-applicant covering 30% of the project activities. The main applicant  in this project is the Roma Education Fund 

	3
	The project team is in place as in the description of action.
	YES
	confirmed

	4
	There is no qualitative or quantitative change in the target groups and final beneficiaries as stipulated in the description of action.
	YES
	The main target groups are the Roma young Women.  

	5
	Activities and results are in line with the description of action.
	YES
	confirmed

	5
	The direct beneficiaries are satisfied with the project and are aware of the objectives of the project.
	YES
	No contact was possible with the final beneficiary during the office visit

	6
	The project team is taking specific steps to ensure the sustainability of the project
	N/A
	Not identified

	
	Actions points presented in the application for Award are executed or in progress 
	YES 
	In progress


PROJECT MANAGER



                                                      Nafi Saracini   29/12/2016
	The application is truthful. It has to be noticed the applicant (KHAM) for the award is only co-applicant in the applying project

	Attached are photos from the visit and other relevant materials



2
1

