
	[image: image1.wmf]
	EUROPEAN UNION

DELEGATION OF THE EUROPEAN UNION  

TO THE REPUBLIC OF SERBIA




MISSION REPORT
Subject: reality check for DG NEAR Roma integration award 2016 application no 3
Date:

13th December 2016, Belgrade
Participants: Mirjana Maksimovic, Project manager (Social inclusion and minorities), Operations I 
Project "Introduction of the Roma language with elements of national culture in primary schools in Serbia" is funded by IPA 2012 EU support to inclusive society project in the amount of 134.832,30 EUR, in total 158.626,24 EUR. Project is implemented since December 2015 until September 2017.
Overall objective of the project is to ensure the social inclusion of marginalised groups and communities with the strengthening of the Roma culture, identity and active socio-economic integration of Roma into society in Serbia. Encouraging interested young people (especially the Roma minority representatives) to acquire new knowledge will enable creation of intellectual elite that comprehensively examines various aspects of the issue. Specific objective is to introduce and implementation of programs for the Roma language teaching in primary schools from 1 - 4th grade in Serbia through the enhancement of the employment and raising capacities of young educated Roma.

Main results are:

· Young educated Roma additionally trained and motivated to implement the teaching of election programs

· To improve knowledge and skills of future Roma language teachers on the methodology and process of teaching 

· To organize accredited training for 40 Roma on the implementation of the teaching elective course 
· Prepared and issued teaching resources for the implementation of the teaching elective course - the Roma language with elements of national culture. Teaching materials prepared and designed. Next phase is printing/publishing and distribution to all targeted schools and students involved in teaching program of Roma language with elements of national culture. 
· Introduced teachers of the Romani language in the education system of primary schools in 15 pilot cities – is not fully achieved (activities are ongoing)
· At least 30 teachers on Roma language with elements of national culture introduced in educational system.

· At least 500 Roma children attending classes on Roma language with elements of national culture
Through this project, for the first time in Serbia, Romani language will be introduced in elementary schools, which is a very important added value. 

I visited the project in CEREZ premises, where class of Romani language was organized for couple of children. Nevertheless, project is dealing with 50 Romani teachers and more than 500 children all around Serbia.

Cc: video material
Prepared by:
Mirjana MAKSIMOVIC                                 
Page 1 of 2
Page 2 of 2

