National Plan of Implementation for Security Council Resolution 1325 of 2000 (Women, Peace and Security)

Palestine

2017-2019

| Strategic Objectives | Policies | Interventions | Activities | Outcomes | Outcome Description | Responsibility | Financial Cost in USD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 1: Enhance the protection of Palestinian women and girls especially against the violations of the Israeli occupation | Policy 1: Improve the quality of the support services for women and girls who suffer violations and gender-based discrimination, especially violence | 1.1 Development and follow up on legal, social, health and mental protection programs for women who suffer any violations and any form of discrimination, especially violence | 1. Carry out a survey to identify the concerned organizations (who offers what? To whom? And where?) | 1. Database of the organizations and their services developed | 1. Development of terms of reference (ToR) that include recruitment of a work team comprised of a main researcher and three assistant researchers to carry out the survey in the West Bank and Gaza Strip through an ad in the official gazette, work team selection committee and signing of a contract and agreement, conducting the research according to the ToR, a workshop to launch the results, printing of survey results. | 1. Ministry of Social Affairs | For TOR development: 1. 2500 USD for the filling out of the questionnaires 2. 5000 USD for the researcher 3. 500 USD for a newspaper ad 4. 1500 USD for holding an expanded workshop 5. 1000 USD for printing Estimated Total = 10,500 USD |
|  |  |  |  | 2. Develop a database involving the security services especially the Military Liaison Office (to include the arrest of women and children, cases of assault, or house or school demolitions) | 2. Development of terms of reference (ToR) that include recruitment of a work team comprised of a main researcher and three assistant researchers to carry out the survey in the West Bank and Gaza Strip through an ad in the official gazette, work team selection committee and signing of a contract and agreement, conducting the research according to the ToR, a workshop to launch the results, printing of survey results. | 2. Ministry of Interior | For TOR development: 1. 2500 USD for the filling out of the questionnaires 2. 5000 USD for the researcher 3. 500 USD for a newspaper ad 4. 1500 USD for holding an expanded workshop 5. 1000 USD for printing Estimated Total = 10,500 USD $ |
|  |  |  | 2. Monitor the reports coming to the Secretariat General of the Council of Ministers from the government departments providing services and build on them to ensure the improvement of the quality of services offered to women and girls. | - Periodic reports are monitored and their impact analyzed, ending with the development of policies and interventions based on what they contained. | Monitoring of and follow-up on reports | Secretariat General of the Council of Ministers, Gender Unit and the Government Performance Quality Unit | Free |
|  |  |  | 3. Development of training guides | 2. A Ministry of Justice procedural legal guide for legal service providers on women who suffer violations and violence. | 2.1 Development of TOR to recruit a specialist in law and violence in order to develop a legal guide. Training of service providers on the guide for a number of hours each day for 4 days involving 30 trainees in a specialized hall. | 2.1 Ministry of Justice | For TOR development: 1. 2500 USD for the filling out of the questionnaires 2. 5000 USD for the researcher 3. 500 USD for a newspaper ad 4. 1500 USD for holding an expanded workshop 5. 1000 USD for printing Total: 10,500 USD For the guide: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 15,000 USD for contracting an expert. 3. 4,500 USD for the workshop hall. 4. 1,000 USD for a focus group. 5. 1000 USD for printing Total: 22,000 USD For the training: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 6,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Total: 7,780 USD Estimated total: USD 40,280 |
|  |  |  |  | 3. Mental, health and social guide | 3.1 Development of TOR to recruit a specialist in health and violence to develop a guide on women who suffer violence in wars. Training service providers on the guide for a number of hours each day for 4 days for 30 trainees in a specialized hall. | 2.2 Ministry of Health | For TOR development: 1. 2500 USD for the filling out of the questionnaires 2. 5000 USD for the researcher 3. 500 USD for a newspaper ad 4. 1500 USD for holding an expanded workshop 5. 1000 USD for printing Total: 10,500 USD For the guide: 1. 500 USD for a newspaper ad for researcher recruitment. 2. 5,500 USD for contracting a researcher. 3. 4,500 USD for workshops. 4. 1,000 USD for a focus group. 5. 1000 USD for printing Total: 22,000 USD For training: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 6,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Total: 7,780 USD Estimated total: USD 40,280 |
|  |  |  | 4. Provision of legal, social, psychological and health support for women and girls who are victims of violations and discrimination, particularly violence | 1. Legal support services offered to women prisoners or those who have suffered violations during incursions and arrests | 3.1 Development of a mechanism to reach women in marginalized areas. | Commission of Prisoners and Ex-Prisoners Affairs | Procedure guide: 1. 500 USD for a newspaper ad for expert recruitment. 2. 5,500 USD for contracting an expert. 3. 4,500 USD for three workshops. 4. 1,000 USD for a focus group. 5. 1000 USD for printing Estimated total: USD 12,500 |
|  |  |  |  |  | 3.2 Publish instructions on the provision of legal service. |  | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  |  |  | 3.3 Publish educational materials for handling Israeli violations legally. | 3.1 Civil society organizations, Commission of Prisoners and Ex-Prisoners Affairs | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  |  | 2. Social support services provided to affected women | 3.2.1 Develop clear instructions for immediate intervention when women suffer violations and are harmed. | Ministry of Social Affairs | Procedure guide: 1. 500 USD for a newspaper ad for expert recruitment. 2. 5,5000 USD for the researcher 3. 4,500 USD for three workshops. 4. 1,000 USD for a focus group. 5. 1000 USD for printing Estimated total: USD 12,500 |
|  |  |  |  |  | 3.2.2 Publish the instructions for the public and raise their awareness of them. | Ministry of Social Affairs | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  |  |  | 3.2.2 Publish educational social materials on how women would handle violations. | 3.2 Civil society organizations | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  |  | 3. Health and Psychological support services provided to affected women | 3.1 Publish clear instructions for where women would go when suffering harm according to the region | 3.1 Ministry of Health | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  |  |  | 3.2 Provide mobile clinics in the areas behind the Wall. | 3.2 Civil society organizations | To be determined by the civil society |
|  |  |  |  |  | 3.3 Publish educational health and psychological materials and how to handle harm. |  | 1. 1,000 USD for radio spots. 2. 5,000 USD for posters. 3. 10,000 USD for billboards Estimated total: 16,000 USD |
|  |  |  | - Enhance the capacities of (male and female) service providers to empower women and girls who are victims of violations and discrimination, especially violence | 4. Capacities of 375 service providers developed on how to handle cases of affected women | 4.1 Training of 25 service providers from the Ministry of Justice, recruitment of a legal trainer, a hall and lunch for two days. | - Ministry of Justice | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.2 Training of 25 service providers in the social affairs sector, recruitment of a trainer in the field of social affairs, a hall and lunch for two days | 4.2 Ministry of Social Affairs | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.3 Training of 25 Ministry of Health staff service providers in the health sector, recruitment of a trainer, a hall and lunch for two days | 4.3 Ministry of Health | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.4 Training of 25 Commission of Prisoners staff service providers. | 4.4 Commission of Prisoners and Ex-prisoners | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.5 Training of 25 persons working in the areas behind the Wall on how to handle Israeli violations legally and service-wise, recruitment of an expert, a hall and lunch for two days. | 4.5 Colonization and Wall Resistance Commission | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.6 Training of 25 persons working in organizations within Jerusalem on how to handle Israeli violations legally and service-wise, recruitment of a trainer, a hall and lunch for two days. | 4.6 Ministry of Jerusalem | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.7 Training of 25 persons working in civil society organizations on how to handle Israeli violations legally and service-wise, recruitment of a trainer, a hall and lunch for two days. | 4.7 Civil society organizations | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.8 Training of 25 persons working in civil society organizations on how to handle Israeli violations legally and service-wise, recruitment of a trainer, a hall and lunch for two days. | 4.8 Ministry of Women’s Affairs | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 4,780 USD |
|  |  |  |  |  | 4.9 Training of 50 persons working in the security establishment (concept of the resolution, resolution localization mechanism in plans, programs, activities and budgets), recruitment of a trainer, a hall and lunch for two days | 4.8 Ministry of Interior | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 9,560 USD |
|  |  |  |  |  | 4.10 Training of 50 persons on the mechanism of documentation of the Occupation’s violations such as attacking women and children in coordination with the Military Liaison Office (Report writing and documentation mechanism), recruitment of a trainer, a hall and lunch for two days | 4.8 Ministry of Interior | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 14,340 USD |
|  |  |  |  |  | 4.11 Raise the awareness of 75 women on the minefields that are prevalent in the West Bank through coordination with Unexploded Ordnance Center at the Ministry of Interior, recruitment of a trainer, a hall and lunch for two days | 4.8 Ministry of Interior | 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 9,560 USD |
|  |  |  |  |  | 1.12 Map the number of legitimate and illegitimate immigration cases abroad through an arrangement between the Department of Arab Affairs and embassies abroad, recruitment of a researcher, a workshop | Ministry of Interior | 1. 5,000 USD for the researcher. 2. 500 USD for a newspaper ad. 3. 1,500 USD for holding an expanded workshop. 4. 1000 USD for printing. Estimated total: 8,000 USD |
|  |  |  |  |  | Coordination meeting to establish a commission for providing services and a coordination commission for all service providers. |  | 4,500 USD for holding an expanded workshop. Estimated total: 8,000 USD |
|  |  |  |  |  | Develop questionnaires and document cases according to professional principles that maintain confidentiality. Activation of the referral system. Take geographic distribution into consideration. Train 120 persons from the West Bank and the Gaza Strip on intervention at times of crises. | Ministry of Women’s Affairs | No financial cost for the questionnaire development. For the training we need 5 training courses: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 3,000 USD to cover the 1,500 USD daily hall fee. 3. 1,280 USD for the trainer’s fee Estimated total: 31,400 USD |
|  | Policy 2: Enhance the steadfastness of Palestinian women and girls under Israeli occupation | 2.1 Development of rights, economic and social empowerment programs for Palestinian women and girls | 1. Activation and development of legislation and policies to enhance the steadfastness of women and ensure their practical implementation. 2. Activation of the Law of the Capital No. 4 of 2002 and ensure its enforcement on the ground. | Law of the Capital activated | 2.1 A decision from the Council of Ministers on the need to put the Law of the Capital into force | Ministry of Jerusalem in coordination with relevant governmental departments and non-governmental organizations | 1. 1*30*50 = 1,500 USD for holding an expanded workshop 2. 1,000 USD for 5 focus groups, 5*1000 = 5,000 USD For the Ministry of Information Printing of 1,000 brochures = 2,000 USD Printing of 1,000 posters and placing them on billboards = 5,000 USD Estimated total: 13,000 USD |
|  |  |  |  |  | 2.2 Create a budget according to the provisions of the Law of the Capital and work to implement it |  |  |
|  |  |  |  |  | 2.3 Create awareness of the Law of the Capital and its importance for the protection of the city through distributing 1000 posters and 1000 brochures. | 2.3 Civil society organizations and the Ministry of Information | - The civil society determines its own budget. - For the Ministry of Information Printing of 1,000 brochures = 2,000 USD Printing of 1,000 posters and placing them on billboards = 5,000 USD Estimated total: 7,000 USD |
|  |  |  | 3. Support the development projects of Palestinian women and girls especially in Jerusalem and the Gaza Strip | 3.1 Mapping of women development projects in areas behind the Wall and direct friction areas. | 3.1 A specialized researcher for the development of a questionnaire to categorize women development projects in friction areas and areas behind the Wall. | 3.1 Ministry of National Economy | 1. 2500 USD for the filling out of the questionnaires 2. 5000 USD for the researcher 3. 500 USD for a newspaper ad 4. 1500 USD for holding an expanded workshop 5. 1000 USD for printing Estimated Total = 10,500 USD |
|  |  |  |  | 3.2 Tax and customs exemption for those projects. | 3.2 A decision from the Council of Ministers on tax and customs exemption for the projects in those areas. | 3.2 Ministry of National Economy |  |
|  |  |  |  | 3.3 Disseminate publicity and advertisement for the products of these projects and encourage their purchase | 3.3 1000 posters, large projection screens, 1000 awareness raising brochures. | Civil society organizations and the Ministry of Information | - The civil society determines its own budget. - For the Ministry of Information Printing of 1,000 brochures = 2,000 USD Printing of 1,000 posters and placing them on billboards = 5,000 USD Estimated total: 7,000 USD |
|  |  |  | 4. Capacity building in project management, marketing and feasibility study for women. | 4.1 Training of 50 women from Jerusalem on project management. | 4.1 A trainer specialized in projects, a hall for 8 days for two courses involving 25 persons in each course. | 4.1 Ministry of Jerusalem | For the training we need two training courses: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 12,000 USD to cover the 1,500 USD daily hall fee. 3. 2,560 USD for the trainer’s fee Estimated total: 15,060 USD |
|  |  |  |  | 4.2 Training of 50 women on project management from the Gaza Strip | 4.2 A trainer specialized in projects, a hall for 8 days for two courses involving 25 persons in each course. | 4.2 Civil society organizations | To be determined by the civil society |
|  |  |  |  | 4.3 Training of 50 women on project management from areas behind the Wall | 4.3 A trainer specialized in projects, a hall for 8 days for two courses involving 25 persons in each course. | 4.3 Colonization and Wall Resistance Commission | For the training we need two training courses: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 12,000 USD to cover the 1,500 USD daily hall fee. 3. 2,560 USD for the trainer’s fee Estimated total: 15,060 USD |
|  |  |  |  | 4.4 Training of 50 women on project management from Area C | 4.4 A trainer specialized in projects, a hall for 8 days for two courses involving 25 persons in each course. | 4.4 Civil society organizations | For the training we need two training courses: 1. 500 USD for a newspaper ad for trainer recruitment. (???) 2. 12,000 USD to cover the 1,500 USD daily hall fee. 3. 2,560 USD for the trainer’s fee Estimated total: 15,060 USD |
|  |  |  |  | 4.5 Training of 50 women ex-prisoners on project management | 4.5 A trainer specialized in projects, a hall for 8 days for two courses involving 25 persons in each course. | 4.5 Commission of Prisoners and Ex-Prisoners Affairs, | For the training we need two training courses: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 12,000 USD to cover the 1,500 USD daily hall fee. 3. 2,560 USD for the trainer’s fee Estimated total: 15,060 USD |
|  |  |  | - Facilitation and provision of grants and soft loans to start income-generating projects for women to enhance their steadfastness, especially in marginalized areas. | 5.1 Map the organizations that provide grants and loans. | 5.1 A questionnaire to be filled out by organizations, recruitment of a main researcher and 3 assistant researchers. | 5.1 Civil society organizations | To be determined by the civil society |
|  |  |  |  | 5.2 Raise the awareness of these organizations of the importance of taking women who suffer violations into consideration | 5.2 1,000 brochures, 1,000 posters. | 5.2 Civil society organizations | To be determined by the civil society. |
|  |  |  |  | 5.3 A policy from the Council of Ministers to ensure the provision of an investment environment that is incentivizing for women who are victims of Israeli violations in small and medium enterprises and another to lower the interest rates for women affected directly by the occupation. | 5.3 Development of a policy paper on enhancing the access of women to resources and sources and subsequently investment in small and medium enterprises and submitting the policy paper to the Council of Ministers. | 5.3 Ministry of National Economy and the Secretariat General of the Council of Ministers | Development of a policy paper: 5,000 USD Estimated total: 5,000 USD |
|  |  |  | - Provide legal counselling and support to Jerusalem women who have suffered occupation violations | 6.1 Create a permanent open hotline for women inside Jerusalem for counselling. | 6.1 Provide qualified staff to work on the hotline. | 6.1 Civil society organizations | To be determined by the civil society |
|  |  | 2.2 Integrate and streamline gender issues into the reconstruction process in the Gaza Strip | - Train and enhance the capacities of target women | 1. Build the capacities of 50 women who work in organizations that have a direct relationship with women. | 1. A trainer on intervention mechanisms and how to work to integrate gender into the reconstruction | 1. Civil society organizations | To be determined by the civil society |
|  |  |  | - Develop studies and working papers and hold meetings and workshops | 2. Develop 3 studies on the situation of women before reconstruction and after reconstruction and provide a fact sheet. | 2. A researcher specialized in reconstruction and the status of women during this phase and three research assistants. | 2. Ministry of Public Works and Housing | 1. 500 USD for newspaper ad for researcher recruitment. 2.1,000 USD for assistant researchers 3. Workshop: 1*30*50 = 1,500 USD Each study is 6,000 USD, so 6,000*3 = 18,000 USD Estimated total: 18,000 USD |
|  |  |  | - Coordination and networking with the reconstruction committees to ensure the participation of target women | 3. Women have been targeted in the reconstruction process | 3.1 Hold 5 meeting with the reconstruction committees. | 3.1 Ministry of Public Works and Housing |  |
|  |  |  |  |  | 3.2 Create awareness among the civil society of the situation of women through 5 workshops. | 3.2 Civil society organizations | To be determined by the civil society |
|  |  |  |  |  | 3.3 Develop a guide on how women benefit from the reconstruction process through a specialist who develops the guide with 3 research assistants and training 30 women on that in a specialized hall for 3 days with full hospitality. | 3.3 Civil society organizations | To be determined by the civil society |
|  |  |  | - Presentation of success stories of women who have participated in the reconstruction programs. | 4. Two stories presented | 4. Identify women who have participated, interview two of them, and address success and difficulties. | 4. Ministry of Public Works and Housing, Ministry of Information | Conduct two interviews on more than one TV station Estimated total: 5,000 USD |
|  |  | 2.3 Develop relief and urgent assistance programs for women and girls who are victims of violations and gender-based discrimination, especially violence | - Creation of appropriate and gender-sensitive shelters | 1. Gender-sensitive reconstruction | 1. Clear instruction from the Council of Ministers on the need for reconstruction to be gender-sensitive in building or distribution of shelters | 1. Ministry of Public Works and Housing | 2 workshop: 2*30*30 = 1,800 USD Estimated total: 1,800 USD |
|  |  |  | - Provision of food and drinking water | 2. Affected women receive food and drinking water | 2.1 Clear instruction from the Ministry of Local Government to local councils on the need for providing drinking water. | 2.1 Ministry of Local Government | 2 workshop: 2*30*30 = 1,800 USD Estimated total: 1,800 USD |
|  |  |  |  |  | 2.2 Monitoring by the Ministry of National Economy of the market and preventing the raising of the prices in any case. | 2.2 Ministry of National Economy |  |
|  |  |  | - Provision for women’s needs | 3. All necessities are available. | 3. Clothes, covers | 3. Civil society organizations | To be determined by the civil society |
|  |  |  | - Provision of cooking gas and electricity generators | 4. Electricity generators and cooking gas are available for all affected women | 4. Map the women who lack cooking gas and electricity generators and provide them with these items | 4. Palestinian Energy Authority | 1. 500 USD for newspaper ad 2. 10,000 USD for the researcher 3. 1*30*50 = 1,500 USD Estimated total: 1,200 USD |
|  |  |  | - Provision of health centers, relief and medical services and basic medicines. | 5. Medical services are available for affected women | 5. Mobile clinics, provision of field doctors, provision of special pharmacies. | 5. Ministry of Health | Estimated total: 150,000 USD |
|  |  |  | - Provision of means of transportation | 6. Means of transportation are secured for affected women | 6. Provision of free cards to affected women for public transport. Provision of a special emergency line for affected women for transport. | 6. Ministry of Transportation | Estimated total: 50,000 USD |
| Estimated total for the First Strategic Objective is 668,700 USD |  |  |  |  |  |  |  |

| Strategic Objectives | Policies | Interventions | Activities | Outcomes | Outcome Description | Responsibility | Financial Cost in USD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 2: Hold the Israeli occupation accountable and prevent impunity in addition to providing reparations for the harm inflicted on Palestinian women and girls in accordance with national and international mechanisms | Policy 1: Work to hold the Israeli occupation accountable nationally and internationally for its crimes against Palestinian women and girls | Strategic Objective 2: Hold the Israeli occupation accountable and prevent impunity in addition to providing reparations for the harm inflicted on Palestinian women and girls in accordance with national and international mechanisms | 1. File and follow up on communications and supplemental briefs with the Office of the Prosecutor of the International Criminal Court | 1. Communications and supplemental briefs and follow up with the Office of the Prosecutor of the International Criminal Court | 1.1 Collection of statistics by the parties working in monitoring and documentation of the crimes committed against Palestinian women and girls by the Israeli occupation. | National Monitoring Center | 100,000 USD for construction Estimated total: 100,000 USD |
|  |  |  |  |  | 1.2 Preparation of the dossiers of the communications and supplemental briefs and their presentation to the competent committee | 1.2 Ministry of Foreign Affairs | The Hague: Six duty assignments for five days, 2 people: 50,000 USD per year 3*50,000 = 150,000 USD Estimated total: 150,000 USD |
|  |  |  |  |  | 1.3 Filing and follow up with the national competent committee | 1.3 Ministry of Foreign Affairs | free |
|  |  |  | - Presentation of the verbal and written interventions and submission of reports regarding the crimes of the Israeli occupation against Palestinian women and girls within the frameworks of the UN bodies: Secretariat, General Assembly, Security Council, Economic and Social Council, | 2. Verbal and written interventions, reports and draft resolutions on the violations of the Israeli occupation against Palestinian women and girls are presented before the main bodies of the United Nations. | 2.1 Raising these issues in the sessions, general meetings and agendas of UN bodies. | 1.2 Ministry of Foreign Affairs | 2.1 duty assignment for five days for 2 people 5,400 USD for one year 3 * 5400 = 162,000 USD Estimated total: 16,200 USD |
|  |  |  |  |  | 2.2 Hold briefing sessions on the status of Palestinian women and girls under the Israeli occupation. | 2.2 Ministry of Foreign Affairs | - 3 duty assignments for one person for four days at a cost of 9,000 USD per year 3*9000 = 27,000 USD Estimated total: 27,000 USD |
|  |  |  |  |  | 2.3 A call for holding special sessions on the violations of the Israeli occupation against Palestinian women and girls. | 2.3 Ministry of Foreign Affairs | 2.3 3 duty assignments for 3 people for four days at a cost of 27,000 USD per year 3*27000 = 81,000 USD Estimated total: 81,000 USD |
|  |  |  |  |  | 2.4 Presentation of draft resolutions before UN bodies to condemn and hold accountable the Israeli occupation for its violations against Palestinian women and girls | 2.4 Ministry of Foreign Affairs | 2.4 2 duty assignments for 3 people for four days at a cost of 1,800 USD per year 3*1,800 = 5,400 USD Estimated total: 5,400 USD |
|  |  |  |  |  | 2.5 Presentation of official reports and letters to call on the UN bodies to pressure the Israeli occupation to adhere to respecting and implementing international law. | Ministry of Foreign Affairs | No financial cost |
|  |  |  |  |  | 2.6 Brief the delegations of the State of Palestine on the status of Palestinian women under occupation | Ministry of Foreign Affairs | No financial cost |
|  |  |  | - Working within the framework of the human rights monitoring system at the UN |  |  |  |  |
|  |  |  | - Treaty-based human rights commissions: Committees on international human rights agreements that the State of Palestine accedes to. | 3.A. Agreements and Conventions that Palestine accedes to are employed for holding the Israeli occupation accountable for the violations it commits against Palestinian women and girls. | 3.A.1. Develop official and shadow preliminary and periodical reports of the agreements showing the violations of the Israeli occupation against Palestinian women and girls. | 3. Ministry of Foreign Affairs, Ministry of Justice, Ministry of Information, and civil society organizations according to competency. |  |
|  |  |  |  |  | 3.A.2 Cooperation and coordination with official and non-official parties that are responsible for the development of reports. |  |  |
|  |  |  |  |  | 3.A.3 Review of the reports |  |  |
|  |  |  |  |  | 3.A.4 Presentation of the reports to the committees concerned with international agreements. | Ministry of Foreign Affairs |  |
|  |  |  |  |  | 3.A.5 Employment of the outcomes of the reports and final remarks issued by the committees concerned with international agreements to hold the Israeli occupation accountable |  |  |
|  |  |  | - Charter-based human rights commissions: - Human Rights Council - Special procedures of the Human Rights Council: Special rapporteurs, independent experts and concerned working teams - Special complaint procedure (1503) | 3.B. Written and verbal reports and data, communications and complaints on the violations of the Israeli occupation against Palestinian women and girls are presented before the charter-based human rights commissions | 3.B.1 Participation in human rights courses, especially through Article 7, and presentation of written and verbal reports and data. | Ministry of Foreign Affairs | 3.b. for the Ministry of Foreign Affairs: 2 duty assignments for 4 people for seven days at a cost of 27,000 USD per year 3*27000 = 81,000 USD Estimated total: 81,000 USD |
|  |  |  |  |  | 3.B.2 Hold briefing sessions with the human rights council |  |  |
|  |  |  |  |  | 3.B.3 Organize parallel events | Ministry of Foreign Affairs | 3.B.3. for the Ministry of Foreign Affairs: 1 duty assignment for 3 people for 4 days at a cost of 7,300 USD per year 3*7300 = 21,900 USD Ministry of Information: 1 duty assignment for 5 people for 4 days at a cost of 12,500 USD per year 3*12500 = 37,500 USD Estimated total: 37,500 USD |
|  |  |  |  |  | 3.B.4 Presentation of communications and complaints in accordance with special procedures and procedure 1503 |  |  |
|  |  |  |  |  | 3.B.5 Networking with special procedures of the Human Rights Council | Ministry of Foreign Affairs | 3.B.5. 1 duty assignment for 2 people for 5 days at a cost of 5,500 USD per year 3*5500 = 16,500 USD Estimated total: 16,500 USD |
|  |  |  | 4. Organize lobby and advocacy campaigns at the international level targeting: - Coalition for the ICC - Commission on the Status of Women (CSW) at the UN - Global Movement for a campaign of Boycott, Divestment and Sanctions (BDS) - International networks of women rights | 4. Public opinion pressuring the Israeli occupation for its non-compliance with international law. | 4.1 Recruitment, mobilization and movement towards these coalitions and networks | 4. Ministry of Foreign Affairs, Ministry of Information, Commission of Detainees and Ex-Detainees Affairs, and civil society organizations according to competency | 1. Ministry of Foreign Affairs: 4.1 2 duty assignment for 3 people for 5 days at a cost of 15,300 USD per year 3*15300 = 45,900 USD - Ministry of Information: 2 duty assignment for 7 people for 5 days at a cost of 35,700 USD per year 3*37500 = 107,100 USD - Ministry of Women’s Affairs: 2 duty assignment for 3 people for 5 days at a cost of 15,300 USD per year 3*15300 = 45,900 USD Estimated total: 198,900 USD |
|  |  |  |  |  | 4.2 Participation in the membership of committees and networks | Ministry of Foreign Affairs | 4.2 Ministry of Foreign Affairs: 1 duty assignment for 1 person for 3 days at a cost of 2,200 USD per year 3*2200 = 6,600 USD Estimated total: 6,600 USD |
|  |  |  |  |  | 4.3 Participation in the annual meeting of the commemoration of the issuance of Resolution 1325 |  | ((Missing text???)) |
|  |  |  |  |  | 4.4 Development of documentary films that show the status of women under the Israeli occupation. | Ministry of Information | 4 documentary films at a cost of 20,000 USD per film Estimated total: 80,000 USD |
|  |  |  |  |  | 4.5 Presentation of verbal and written reports and memoranda to all levels showing the violations of the occupation against Palestinian women and girls |  |  |
|  |  |  | - Mobilize regional and international support, support the efforts of the Palestinian state to hold the occupation accountable, secure the needed support and draft relevant announcements and memos | States’ respect for their commitments | Call on states through the delegations that visit Palestine to fulfill their obligations in accordance with international law | Prime Minister |  |
|  |  | Intervention 2: Activation of national accountability and protection mechanisms against the perpetrators of crimes. | - Urge and demand that third party states fulfill their obligations in accordance with international agreements. | - Third party states respect and ensure the respect of their commitments in accordance with international agreements. | 1. Call upon the states through their embassies and representative offices to fulfill their commitments in accordance with international law. | 1. Ministry of Foreign Affairs |  |
|  |  |  |  |  | 1.2 Participation in conferences of the states that are party to the agreements and demand the fulfillment of their obligations in accordance with international law. | 1.2 Ministry of Foreign Affairs | 1.2 Ministry of Foreign Affairs: ??? duty assignments for 3 people for 4 days at a cost of 22,000 USD per year 3*22000 = 66,000 USD Estimated total: 66,000 USD |
|  |  |  |  |  | 1.3 Call upon the states to pay their dues to the specialized commissions and agencies working on the Palestinian cause. | 1.3 Ministry of Foreign Affairs, Ministry of Information, and civil society organizations | 1.3 Ministry of Foreign Affairs: ??? duty assignments for 1 person for 3 days at a cost of 6,600 USD per year For coverage by the Ministry of Information, five people are required = 5*6,600 = 33,000 USD Estimated total: 118,800 USD |
|  |  |  |  |  | 1.4 Work and coordinate with the expatriate Palestinian and Arab communities | 1.4 Ministry of Foreign Affairs and civil society organizations |  |
|  |  |  | - Bring cases before national courts on the basis of the international criminal jurisdiction. | 2. Cases pending before national courts on the basis of the international criminal jurisdiction. | 2.1 Preparation of case files | 2.1. Civil society organizations in coordination with the Ministry of Foreign Affairs |  |
|  |  |  |  |  | 2.2 Contract a specialized legal team and provide it with all facts and information and cooperate with it. |  |  |
|  |  |  |  |  | 2.3 Follow up on filed cases | 2.3 Ministry of Foreign Affairs | 2.3 2 duty assignments for 2 people per task per year for ??? days at a cost of 12,500 USD per year 3*12500 = 37,500 USD Estimated total: 37,500 USD |
|  |  |  | 3. Organization of lobbying and advocacy campaigns at the regional and national levels that target: - Arab Women Organization - Arab Human Rights Committee (Charter committee) - Arab Women Unions - Women committees in national and Arab parliaments - Regional networks concerned with women rights | 3. A national and regional public opinion pressuring the Israeli occupation for not complying with international law. | 3.1 Recruitment, mobilization and movement towards these coalitions and networks | 3. Ministry of Foreign Affairs, Ministry of Information, civil society organizations according to competency, Ministry of Prisoners and Ex-prisoners Affairs | 3.1 Ministry of Foreign Affairs: 1 duty assignment for 2 people for 5 days at a cost of 4,100 USD per year 3*4100 = 12,300 USD For the Ministry of Information: 1 duty assignment for 5 people for 5 days at a cost of 10,500 USD per year 3*10,500 = 31,500 USD Estimated total: 43,800 USD |
|  |  |  |  |  | 3.2 Participation in the membership of these networks and committees |  | 3.2 Cost for the Ministry of Foreign Affairs: 1 duty assignment for 2 people for 3 days at a cost of 4,300 USD per year 3*4300 = 12,900 USD Estimated total: 12,900 USD |
|  |  |  |  |  | 3.3 Presentation of verbal and written reports and memoranda to all levels showing the violations of the occupation against Palestinian women and girls |  |  |
|  | Policy 2: Enhance the organizational capacities pertaining to the monitoring mechanisms and documentation relating to the enforcement of the themes of resolution 1325 | Intervention 1: Adoption of a standard national system to monitor and document issues in relation to the enforcement of the themes of the Resolution. | - Build capacities on the basis of UN guides especially the Training Manual on Human Rights Monitoring | 1. Capacities of organizations working on monitoring developed | 1. Five training courses with each course lasting four days, specialized trainer, a hall, and hospitality. | 1. Ministry of Women’s Affairs | For Training: 1. 500 USD for a newspaper ad for trainer recruitment. 2. 15,000 USD to cover the 1,500 USD daily hall fee. 3. 6,400 USD for the trainer’s fee Estimated total: 23,400 USD |
|  |  |  | 2. Develop national monitoring and documentation mechanism on the basis of international mechanisms and their developments | 2. Monitoring mechanisms standardized | 2. Map the organizations working on monitoring, study of the forms, and a specialist to standardize the forms. | 2. Ministry of Women’s Affairs | Estimated total: 129,000 USD |
|  |  |  | 3. Formulate and approve the standard national system duly | 3. National system is approved | 3. Five workshops with the partners to discuss the system, a hall, and hospitality. | 3. Ministry of Women’s Affairs | 5*1500*25 = 18,750 USD Estimated total: 18,750 USD |
|  |  | Intervention 2: Creation of a national monitoring center to monitor and document information related to the enforcement of the themes of Resolution 1325 | - Formation of a technical participatory committee comprised of competent parties to develop the work procedures of the Monitoring Center and ensure its independence. | 1. A technical committee formed to develop the Monitoring Center’s procedures | 1. Send invitations to organizations for membership according to competency, identify the work tasks of the committee | 1. Ministry of Women’s Affairs |  |
|  |  |  | - Coordination and networking for receipt, documentation and categorization of monitoring data in databases and sending them to the concerned parties. | 2. Data has been collected and analyzed | 2. Electronic data collection system, specialized researcher for analysis | 2. Ministry of Women’s Affairs | Purchase of an electronic data collection system: 5,000 USD Estimated total: 5,000 USD |
|  |  |  | 3. Development of annual reports and when needed, country and thematic reports, on the information and data related to the themes of the Resolution 1325 | 3. Reports published on the situation based on the monitoring data | 3. Obtain data from the monitoring center, a researcher specialized in developing preliminary reports. | 3. All organizations based on competency | Specialized researcher’s monthly fee: 1,000 USD So, 1000*12*3 Estimated total: 36,000 USD |
| Estimated total for the Second Strategic Objective is 1,429,850 USD |  |  |  |  |  |  |  |

| Strategic Objectives | Policies | Interventions | Activities | Outcomes | Outcome Description | Responsibility | Financial Cost in USD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Objective 3: Enhance the participation of Palestinian women in the decision-making processes locally and internationally | Policy 1: Develop and increase the representation of Palestinian women at the leadership level in governmental and non-governmental institutions and support their participation in international organizations | 1. Support and empower women in decision-making positions especially in: - Main UN bodies - Peacekeeping and international security operations - UN human rights monitoring system - Decision-making positions locally at the level of legislative, executive, and judicial powers and the civil society | 1. Lobby decision makers to remove obstacles to the progress of women | 1.1 An annual media campaign targeting 50% of the decision makers | 1. Brochures (300), Posters (300), radio spots (3). | 1. Civil society organizations, Ministry of Information | Brochures: 2,000 USD Radio spots: 3,500 USD for purposes of development and broadcasting Brochures: 5,000 USD Estimated total: 10,500 USD |
|  |  |  |  | 1.2 Central rallies to lobby for the participation of women in decision-making processes | 1.2 Formation of groups in the governorates, writing invitations for the rally, raise placards (5 in every governorate) and 50 banners in every governorate. | 1.2 Civil society organizations | To be determined by the civil society |
|  |  |  |  | 1.3 Memoranda and petitions for the participation of women (at least two local memoranda). | 1.3 Two local memoranda, collection of signatures from all institutions, submitting them to the government. | 1.3 Civil society organizations | To be determined by the civil society |
|  |  |  |  | 1.4 Build the capacity of the female members of the local and municipal councils to enable them to access decision-making positions (Musharaka (Participation) Project 2013-2016. |  | 1.4 Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  |  | 1.5 Support female members of the local and municipal councils through providing them with financial grants for implementing initiatives in their locations (Sustainable empowerment and empowering Palestinian women to participate in political life project 1/2016 – 9/2016). |  | 1.5 Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  | - Lobby for the appointment of Palestinian women as special envoys to offer their good offices and as good will ambassadors | - Palestinian women are participants in the decision-making process at the local and international levels. | - Palestinian women are participants in the decision-making process at the local and international levels. - Nominate Palestinian women to assume decision-making positions at international organizations and bodies. - Urge countries to vote in favor of Palestinian women to assume decision-making positions at international organizations and bodies. - Address and urge the UN Secretary General to appoint Palestinian women as special envoys to offer their good offices and as good will ambassadors | - Ministry of Foreign Affairs | One duty assignment for one person for 4 days, at a cost of 4,000 USD per year 3*4,000 = 12,000 USD Estimated total: 12,000 USD |
|  |  |  | 3. Development of policy studies and statistical indicators relating to the participation of women in decision-making position with regular follow up on them | 2. One annual study | 2. Contract a researcher, develop a report, workshop | 2. Palestinian Central Bureau of Statistics | - Newspaper ad: 500 USD - For the researcher: 10,000 USD - Workshop = 1*30*50 = 1,500 USD Estimated total: 12,000 USD |
|  |  |  | 3. Develop and approve national legislation and policies that ensure the increase of the percentage of representation of women in international decision making positions | 3. Percentage of women in decision-making positions is 30% | 3. Policy paper for the Council of Ministers in this regard | 3. Ministry of Women’s Affairs and the Secretariat General of the Council of Ministers | Policy paper: 5,000 USD Estimated total: 5,000 USD |
|  |  |  | 4. Urge international organizations and commissions to integrate Palestinian women into decision making positions | 4. The projects of international organizations aim to increase the representation of women in decision-making | 4. Two workshops through the Local Aid Coordination Secretariat (LACS), addressing international organizations with an official letter | 4. Ministry of Women’s Affairs | 2*100*40 = 8000 NIS, which is equivalent to 2,200 USD Estimated total: 2,200 USD |
|  |  |  | 5. Address and urge the UN Secretary General to appoint Palestinian women as special envoys to carry out good offices and be good will ambassadors | 5. Palestinian women are special envoys and good will ambassadors | 5. Hold 5 meetings to identify the women and their number; submit a memo to the UN Secretary General in this regard | 5. Ministry of Foreign Affairs |  |
|  |  |  |  |  | 5.2 Training 50 women on leadership in international and diplomatic work, specialized trainer, two courses, each course lasts 3 days, a hall, and hospitality |  | For training: - Newspaper ad for the recruitment of a trainer: 500 USD - Hall = number of workshops *price of meal * number of people * number of days = 2*30*50*6 =18,000 USD - Trainer: 8*40*6 = 1,920 USD Estimated total: 20,420 USD |
|  | Policy 2: Enhancement of the role of Palestinian women in maintaining the civil peace and supporting national unity | 2. Involvement of Palestinian women in the committees and dialogues of the Palestinian reconciliation | - Spread community awareness to enhance the reconciliation and civil peace | 1. Three meetings annually in every governorate with the grassroots organizations, parties and local councils to enhance civil peace | 2. Two facilitators for meetings and workshops, a hall, and media coverage. | 1. Ministry of Information, civil society organizations | - For the Ministry of Information Hall = number of meetings = meal cost * number of people * number of days = for every meeting 1*30*50*3 = 9,000 - Facilitator: 8*40*3 = 960 USD Estimated total: 9,960 USD |
|  |  |  | 2. Lobby the political parties to ensure the participation of women in in the committees and dialogues of Palestinian reconciliation | 2.1 Women participate in the committees and dialogues of the Palestinian reconciliation | 2.1 Addressing the parties on the need to involve women in the reconciliation committees, allocation of 2 seats for women from each party in the reconciliation committees. | 2. Ministry of Information, civil society organizations |  |
|  |  |  |  | 2.2 Build the capacities of young leaders in the party grassroots in 20 locations in the West Bank and the Gaza Strip on the concepts of building civil peace, leadership, conflict resolution, and initiative (My Right to My Future Project 2015-2017). |  | 2.2 Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  |  | 2.3 Working with the political parties to develop work plans to implement the honor charter that the Women's Affairs Technical Committee (WATC) signed with 12 political parties. The plans include increasing the representation of women in parties and in decision-making positions (My Right to My Future Project 2015-2017) |  | 2.3 Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  |  | 2.4 In cooperation with UNWOMEN, work is ongoing currently on documenting the success stories of women activists such as local authority members and members of the local lobby group in Gaza. (Musharaka (Participation ) Project 2013-2016) |  | 2.4 Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  | - Presentation of stories of suffering by Palestinian women as a result of the division or the loss of civil peace. | 3. Five stories presented annually. | 3. Prepare women and meet them. Invitation for an open day to present the stories. | 3. Ministry of Information, civil society organizations | For coverage for the benefit of the Ministry of Information = 5,000 USD Estimated total: 5,000 USD |
|  |  | Development of school and university curricula in a manner that enhances the role and participation of women in civil peace | - Development of research studies and papers and statistical indicators on the degree of curricula’s sensitivity to the values of equality, non-discrimination, participation, respect for the other and concepts of civil peace. | 1. A database on the educational curricula and their suitability to gender issues | 1. Database, contracting a main researcher, development of questionnaires, targeting all the country, and data analysis. | Ministry of Education and Higher Education |  |
|  |  |  | - Modification of Palestinian curricula in a manner that ensures the elimination of all forms of discrimination against women and their role in achieving civil peace. | 2. Curricula that are sensitive to gender issues especially the elimination of discrimination and the role of women in civil peace. | 2. Identification of the curricula that would be modified, identification of the issues that would be added or developed, hold three workshops to discuss the modifications, write up a policy paper on the issues that would be considered. | 2. Ministry of Education and Higher Education |  |
|  |  |  | 3. Enhance the participation of Palestinian women and girls in student councils at Palestinian universities. | 3. Female students participate in student councils | 3. A paper on the obstacles to the participation of female students in student councils, holding meetings with students councils and educating them on the importance of the participation of female students, urge the student blocs to nominate female students to membership in the student councils. | 3. Civil society organizations | To be determined by the civil society |
|  |  | Create platforms for permanent dialogue between Palestinian women and girls to enhance the values of tolerance and national unity | - Hold regular meetings and dialogues among Palestinian women especially women leaders from the various party cadres and community organizations | 1. Regular meetings held among all the party cadres to enhance civil peace especially for women | 1. Three meetings annually, invitation to the parties to talk about the internal conditions and enhance the internal front and urge the parties to publish documents that support civil peace | 1. Civil society organizations, Ministry of Information, media organizations, political parties, and the coalition. | For the benefit of the Ministry of Information: - Coverage = 5,000 USD - Three workshops = 3*30*50 = 4,500 USD Estimated total: 9,500 USD |
|  |  |  | - Demand that party cadres and community organizations adopt the outcomes of the regular meetings and dialogues | 2. Dialogue outcomes are adopted by the parties guaranteeing the enhancement of civil peace, lobby and advocacy campaigns and individual meetings with the Minister of Foreign Affairs to enhance the participation of women in decision –making processes | 2. Signing of a memorandum of understanding among the parties pledging to adhere to the values of civil peace and guaranteeing women rights, a hall, a press conference | 2. Women's Affairs Technical Committee (WATC) | Determined by the staff in accordance with the annex of this plan. |
|  |  |  | - Urge the audio-visual and print media and social media activists to adopt the concepts of tolerance and national unity as priorities in the various programs, activities and informational publications | - Concepts of tolerance and national unity are adopted into the media discourse | 3. Signing of a memoranda of understanding between the media organizations on the adoption of the concepts of tolerance and national unity into the media discourse, map the media organizations, hold a workshop for media organizations, a hall, and hospitality. | 3. Ministry of Information | 1*30*50 = 1,500 USD or the hall Estimated total: 1,500 USD |
|  |  |  | 4. Enhance the role of Palestinian women working in the media in their efforts aimed at achieving national unity | 4. 100 female media professionals and 100 male media professionals are trained on the concepts of tolerance and national unity | 4. Recruit a trainer specialized in media and the concepts of tolerance and national unity, 8 training courses per year with each course being 3 days long, a hall, and hospitality. | 4. Civil society organizations | To be determined by the civil society |
|  |  |  |  | 4.1 Formation of media coalition of media organizations and women media organizations | 4.1 Implementation of a capacity building exercise for the members of the coalition on gender and political participation concepts. | 4.1 Ministry of Information, Women’s Affairs Technical Committee | For the Ministry of Information: For Training: There is a need for a 5-day training for 25 people in the training course For the hall = 5*30*25 =3,750 USD For the trainer: Newspaper ad:500 USD Training = 2*40*8*25 = 8,500 USD Estimated total: 12,750 USD |
| Estimated total for the Third Strategic Objective is 100,830 USD |  |  |  |  |  |  |  |

Note: The annexes of the plan are an integral part of it.