## Foglio1
ISO 9001-2015 – Seven Month Plan
Task or Task Group | Process | Team Specialist | Team WD | SME Internal Resource | Dec | Jan | Feb | Mar | April | May | June
Assessment of Legal Requirements and Perform Gap Analysis. Meeting with top management of the organisation. Initial context analysis, identification of the stakeholders, identification and categorisation of processes. Organisational structure of the organisation, organisational chart, responsibilities. Customer focus. | General Management | bar: Dec
Team meeting to start preparation of the technical assistance. | bar: Dec
Sharing of Gap Analysis Findings and ISO Project Implementation Timetable with the Organisation's Top Management | General Management | bar: Dec
First Steering Team Meeting and Assign Team Members | bar: Dec
Train Team Members | bar: Jan
Organisational structure, responsibilities (5.3), Detailed context analysis (4.1), identification of the stakeholders (4.2), risk analysis and draft SWOT and risk analysis documents (6.1). | General Management | bar: Jan to Mar
Map of the processes operated by the Organisation (4.4) | General Management | bar: Jan to Mar
Introduction of the PDCA method for planning (6.1) and changes (6.3). | General Management | bar: Jan to Mar
Commitment of top management to quality and customer focus (5.1). Definition of the scope of the organisation and certification (4.3), quality policy (5.2) and quality objectives (6.2). Organisation of the management review (9.3). | General Management | bar: Jan
Development and update of documented information to establish the QMS, Keeping Records /Documented Information to be retained to provide evidence of results achieved (7.5.1, 7.5.2), including Procedures, Forms, Flow Charts necessary to improve the QMS | Quality Control | bar: Jan to Feb
Control of documents information (7.5.3) | Quality Control | bar: Jan to May
Human Resources (7.1.2), analysis of competence (7.2), awareness (7.3), organisational knowledge (7.1.6) and Training. | Administration | bar: Jan to April
Other support activities including Infrastructure and Environment (7.1.3 and 7.1.4) | Operations | bar: Feb to April
Communication (7.4) | General Management | bar: Jan to May
Operational Planning and Control (8.1) | Operations | bar: Jan to April
Requirements for Products and Services (8.2, 8.6), Post Delivery Activities (8.5.5) and Release of Products and Services (7.6). | Operations | bar: Feb to Mar
Design and Development of Products and Services (8.3). | D&D | bar: Jan to April
Control of Externally Provided Processes, Products and Services (8.4). | Procurement | bar: Jan to April
Production process (8.5), including Control of Production and Service Provision, Identification and Traceability, Customer Property, Preservation of Product, Control of Changes. Own farm for production of raw materiale. | Operations | bar: Jan to Mar
Improvement (10.1 and 10.3) | Quality Control | bar: Jan to April
Control of Nonconforming Outputs (8.7) and Corrective Actions (10.2) | Quality Control | bar: Jan to April
Control of Measuring and Monitoring Devices (7.1.5) | Quality Control | bar: Jan to Mar
Monitoring, Measuring and Analysis of Customer Satisfaction (9.1.2) | Quality Control | bar: Jan to April
Internal Audits (9.2) and quality control and assurance, analysis and evaluation (8.7, 9.1.1, 9.1.3) | Quality Control | bar: Jan to April
Start Internal Audits | bar: May
Hold Management Review | bar: May to June
Train employees After Internal Audit Findings if necessary | bar: May
Run system as each team completes, total system running | bar: May to June
Certification/Registration Audit | bar: June
TOTAL WD |  |  | 0