## Slide 1: Review on the German Data Collection Process during the Global Monitoring Round 2015-2016
Date: 02-03-2018 Speaker: Lisa Royaee (BMZ Department: Effectiveness & Transparency, Quality Standards)

## Slide 2: Content
The Global Monitoring Round 2015/16
The Decentralized Data Collection Process in the German System
Main Findings on Strengths and Weaknesses of the Process
Lessons Learnt for the Data Collection Process 2018

## Slide 3: The Global Monitoring 2015/2016 in German Development Cooperation
1.37 billion US Dollar of German ODA spending captured by Global Monitoring
43 partner countries participated, of which 21 partner countries in fragile contexts
Direct feedback from external structure: Complex process and difficult implementation
External Consulting Report „Analysis of the German experiences during the Global Monitoring of the Effectiveness Agenda“ November 2016

## Slide 4: The Decentralized Data Collection Process in 2015/2016
GIZ – Technical Cooperation
KfW – Financial Cooperation
BMZ Representative in Partner Country
National Coordinator at Partner Country Level
Indicators 1, 5a, 9b
& 5b, 6
Indicators 1, 5a, 9b
& 5b, 6
Support from BMZ headquarter
Central instruction document explaining the indicators‘ application on German System
German help desk
Partly via Foreign Office
Notes: BMZ Representatives are commissioned by the Foreign Office
BMZ representatives do not have direct access to data but rely on data of implementing organizations – Data quality eventually depends on cooperation between actors
Central Instruction Document = Ausfüllhilfe

## Slide 5: Strengths of the Data Collection Process
Early communication through headquarter to announce the Global Monitoring
Central Instruction Document to explain the indicators‘ interpretation for the German system
German Help Desk
Report assessing the final results of the Monitoring results for Germany
  Aggregated Results for Germany
  Results per Partner Country

## Slide 6: Weaknesses & Challenges of the Data Collection Process I
Scarce Capacities, especially true in fragile contexts
Unclear Definition of Roles and Responsibilities among German actors
Inefficient Communication among numerous actors in a complex process
Adaptation of the indicators on German System, e.g. technical cooperation is difficult to be displayed

## Slide 7: Weaknesses & Challenges of the Data Collection Process II
Changing indicators and framework: process with little continuity
Lacking Understanding of goal, potential and value of Global Monitoring exercise among German external structure – impression intensified by late / little follow up communication about results (Analysis report end of 2017)
Leading to general questioning of validity of Monitoring results

## Slide 8: The Way Forward: Lessons Learnt for the Data Collection Process 2018
Four Objectives:
Raise interest and coherently inform on objectives and potentials of the Global Monitoring (communication strategy)
Provide clear guidance on the process, the next steps as well as on roles & responsibilities
Provide clear guidance on meaning and interpretation of the indicators for German development cooperation
Be an available, reliable contact for questions and support

## Slide 9: The Way forward: Lessons Learnt and Adaptation for the Data Collection Process 2018
Possible Activities:
Preparation
Data Collection
Follow Up
Announce, inform, encourage Idea: Pre-Monitoring Skype Conferences | Central instruction document Online help desk Regular updates: keep interest high | Feedback form for actors involved Share Follow Up Information and final results Analyze the results for Germany, draw conclusions for Cooperation System

## Slide 10: Conclusion
Complex process with many actors involved requires systematic preparations, clear communication and guidance
Global Monitoring Framework vs. peculiarities of donor systems will persist
Thorough framing of the Monitoring exercise is key to raise interest and motivate
Using the results as a basis for discussion in view of improving effectiveness is important

## Slide 11
Thank you for your attention!