|  | EUROPEAN COMMISSION EuropeAid Co-operation Office Quality of Operations |
| --- | --- |

Brussels, 25 October 2007

“Developing a EuropeAid strategy to meet the EU aid effectiveness targets on Technical Cooperation and Project Implementation Units”

# Questionnaire for the 46 delegations members of the Aid Effectiveness Network

Background and purpose In July 2007, EuropeAid launched the preparation of a new strategy to improve the quality of its Technical Cooperation and of the implementation arrangements of its projects. The approach and work plan are described in the Terms of References. Learning from the Delegation's experiences is essential to the success of this initiative and this survey is the major component of the preparation of our strategy. The objectives of the survey include : - To serve at Delegation level as a starting point for : i) stocktaking on current practices ; ii) structuring an internal discussion on how to improve quality and meet EU targets - To provide us with your contributions into the development of our strategy on TC and PIUs. - To promote exchange of practices among members of the network (see below features of the "D- Group facility") Answering this survey is a first step towards enhancing the quality of TC provision and project implementation arrangements. Your views will be key to addressing the potential "areas of change" that we have pre-identified for the development of the forthcoming strategy (see areas shown in red in the matrix attached in annexe 1). The questionnaire has been reviewed by the EuropeAid Working Group on TC – PIU and at delegation level. It has been estimated that two/three hours of work may be needed to fill it in. In line with the objective of using the survey as a first step towards better practices, we strongly suggest to prepare the reply through team work/internal meetings. The Head of Operations – as members of the network - may coordinate the preparation of the final reply. For regional delegations, questionnaires should be filled up by country. The questionnaire can be filled up in French or in English. The DEADLINE for reply is the 16 November 2007. A feed-back document, summarising the essence of your replies, will be transmitted to the Network in early December. Filled up questionnaires should be sent to the functional box : “AIDCO E5 Survey on TC-PIU”. The D-Group Facility, organisation and contact To foster intra-network communication among the Delegations members of the Aid Effectiveness Network, the survey will be managed through a "Discussion - Group facility" (D-Group). Each member of the Group will automatically receive by e-mail the replies to the survey sent by the other delegations. All filled up questionnaires will be accessible on the D-Group site.. The Head of Operations members of the AE network are automatically registered as members of the D-Group. We recommend that any person in delegation interested on these topics become member of the Group addressing a demand to the functional box : "AIDCO E5 Survey on TC-PIU". The D-Groups Facility site contains selected documentation on TC and PIU issues under the menu "resources" and will be utilized again to support communication in the coming phases of the preparation of the strategy For additional information, please do not hesitate to contact either Virginia Manzitti or Felice Zaccheo at Unit E5, in charge of the preparation of the strategy.

PARIS and EU targets in the area of TC and PIU

Definitions

Box 1 a) : The aid effectiveness targets on TC and PIUs

The Paris Declaration has 12 indicators of which 2 are designed to monitor the use of TC and PIUs. The EU has agreed on two more ambitious complimentary indicators on these two issues: Indicators on TC : Paris Declaration - Indicator 4: “50% of TC flows are implemented through coordinated programmes consistent with national development strategies”. EU’s target : “to provide all capacity building assistance through coordinated programmes with an increasing use of multi-donor arrangements”. Indicators on PIUs : Paris Declaration - Indicator 6: “to reduce by two-thirds the stock of parallel implementation PIUs”. EU target : “to avoid the establishment of new PIUs” .

Box 1 b) : Working definitions of TC and TA

There are many definitions for the terms ‘technical cooperation’ and ‘technical assistance’. For the purposes of this exercise,  we have adopted the definitions used by the OECD-DAC for the monitoring of the Paris declaration:

Technical cooperation (TC) is the provision of know-how in the form of personnel, training, and research and associated costs. It comprises activities that augment the level of knowledge, skills, technical know-how or productive aptitudes of people in developing countries, AND services such as consultancies, technical support or the provision of know-how that contribute to the execution of a capital project.

TC thus includes a range of activities, including long and short-term TA*, training, research, twinning, peer-support etc.

*In this questionnaire The term Technical assistance (TA) is used to refer only to the personnel involved in these activities

Structure of the questionnaire

Part I: Mapping of long term technical assistance Part II: Exploring current practices and options for the future A. Completing the picture: Technical cooperation in the EC’s assistance portfolio B. TA design in project/programme formulation C. Tendering and procurement of TA D: Implementation of TA E: Evaluation of TC/TA F. Questions on PIUs G. Role played by the partner government H. Donor coordination on TC/TA and PIUs I. Looking forward and collecting your ideas on the future strategy

PARIS and EU targets in the area of TC and PIU

Definitions

Country: Bangladesh

Part I: Mapping of long term technical assistance

The table below is intended to provide a basic mapping of main long-term TA currently posted in major programmes in your country. Please use it to screen  long term TA in  the "top 5 programmes"  currently under implementation  (including GBS, SPSP, projects ). Refer to Box 2 on page 4. There are more detailed questions on some of the aspects listed here in Part II of the questionnaire.

Table 1: Long term technical assistance

|  | Case 1 | Case 2 | Case 3 | Case 4 | Case 5 |
| --- | --- | --- | --- | --- | --- |
| - Short Project/ Programme title | HNPSP (SWAP in Health, Nutrition, Population, sector programme) | PEDP-II Primary Education Development Program (PEDP-II) SWAP (CRIS Decision 5813) | CHTDF: Promotion of Development and Confidence Building in Chittagong Hills Tracts Governance | Vulnerable Group Development for Ultra-Poor (VGDUP) (CRIS 17631) Food Security | Bangladesh Trade Support Programme (BTSP) (CRIS Decision no. 5823) |
| - Financing modality | SBS/PF/P 1) Financed by a bilateral donor in agreement with all health donors 2-3) Financed from pool fund 4) Bilaterally provided in kind | SBS/PF Grant pool fund of 6 partners + 2 development loans (ADB and IDA) + 2 parallel funding activities, under the umbrella of an 11-member consortium. (=PF) | PF Project- Joint Management with International Organization (UNDP) (EC contribution in 2 phases EUR 23 million) | P | P Project (EC contribution 7.8M Euro and GoB contribution 700,000 Euro) |
| - Description of the TAs component | Long term provision of experts for substituting unavailable capacity and to facilitate the capacity building process in the Ministry of Health It provides long term TA for various areas: 1) TA to Financial Management Unit 2) Programme Support Office – a unit to support the health ministry in managing the sector programme 3) Two further units in the health ministry for contracting non-state service providers 4) Support to two units working on diversification of health financing and the Health Information System | There are 3 components: a) TA integrated in the Program Coordination Unit (PCU=PIU) and in different line units of the Government (around 50 posts; 50% national); b) A Program Liaison Unit (PLU) managed by ADB on behalf of the Consortium, for constant program monitoring and program guidance, and for reporting to the Donor Consortium (10 posts, mostly national); c) Additional TA by individual experts, provided by several development partners (5-6 international posts, incl. 2 posts provided by EC) | UNDP (managing many stakeholders) | 3 long-term positions (1 international, 2 local) | The project has 4 components which are managed by a horizontal component. Component 1: Bangladesh Foreign Trade Institute, 2 types of TA, International ST and Twinning TA (yet to start). 9 senior staff to be recruited Component 2: MoC: Int'l TA through FWC and local TA through local contracting. 8 studies = 632 d International and 1154d local TA. 3. Component 3: Tariff Commission: ST Int'l TA 15mm and local Experts 10mm. Approx. 10 activities 4 Shipping Component: Int'l TA.22 activities, 42 int'l TA and 50 local TA. All local TA contracted through local contract with PTF. 5. Horizontal component: includes an ETAT Leader LT contract, local Programme Director, Accounting Officer, and other staff for the PTF. |
| - Are the TAs part of or linked to a PIU? | Yes | a) The PCU is integrated in the education administration (=YES) b) The PLU is managed by ADB on behalf of the Donor Consortium (=NO). c) Additional TA provided by Development partners is usually linked to the PLU, but not organizational part of it (=NO). | Yes they are part through the project steering committee | yes | a) The LT ETAT support is directly part of PIU b) All other TA contracts are also working directly with the PTF (Project Task Force). (=Yes) |
| - Type of role(s) played by TAs | a) Substitution b) Supporting capacity development | a) Overall program guidance, policy advice, monitoring + specific advice in different program components (integrated in government line units) (=1, 2, 3, 4, 5, 6; no Imprest responsibility) b) external monitoring (finance flows from DPs, budget execution, progress indicators) (=1, 4, 5; Imprest accounting done by ADB with support from PLU) c) usually short-or mid-term TA following specific needs addressed by the Government (e.g. infrastructure, inclusive education) (=2, 4, 5; no imprest responsibilities). | 2, 3, 6 (and 4) | -advisory work to partner government - training - implementation monitoring 3,6,2 | a) Overall program guidance, policy advice, monitoring + specific advice in different program components (integrated in government line units) (=1, 2, 3, 4, 5, 6; no Imprest responsibility, Imprest accounting done by Accounting Officer) |
| - Centralised or decentralised management | Centralised – i.e. financed from pool fund | a) Fully decentralized. Procurement of services through Govt. Line of Responsibility to Government (=B). b) Decentralized in the sense that management responsibility is given to ADB by all other consortium partners (=B?). c) Centralized in the case of EC-funded TA: reporting directly to Delegation. Similar in other cases (DFID, SIDA). (=C) [N.B. the categories are EC-specific and cannot be fully applied to a SWAP] | Centralised | A and B | A. de-centralised management with ex-ante control. |
| - Level of partner government involvement | High – Apart from No. 1 and 4 above, all long term TA was contracted through Gov procedures | a) Line of responsibility of TA is to the Program Director and to the Joint Program Director (both government officials) (=high); b) As a monitoring unit, the PLU is completely independent of the government (=low); c) While the individual experts work closely with their government counterparts, the line of responsibility is to the contracting agency (=low). | MEDIUM | low | a) Level of involvement and leadership by the partner government in the design, selection and management of the long term TA is low. b) While the individual experts work closely with their government counterparts, the line of responsibility of the beneficiary varies from person to person. |
| - Who do TAs report to in practice? | Apart from 4, where the role may be somehow ambiguous, all TA reports to Government | a) TA reports to government. Reports are then cleared/modified and shared as government reports with development partners (=PG); b) PLU staff reports to ADB who then report officially to the other development partners (=Del.?); c) TA reports directly to contracting authority, reports are usually immediately shared with PLU and, where appropriate, with government (=Del.). | DEL and government | PG and Del | a) LT TA Reports problems to the Delegation. b) ST TAs reports to government counterparts responsible for the studies, PTF and the Del. c) For contract related issues the ST TAs report to the Delegation and the PTF. |
| - TA quality | Del. View: referring to row 1 above the quality of the different unit is perceived to differ: 1) adequate 2) inadequate 3 - 4) | a) There have been complaints by government about cultural insensitivity and lack of country experience by international consultants, leading to high staff turnover. There is increasing pressure from the government and lately also civil society to recruit local TA. This has been perceived as a quality loss by some donors (=inadequate) b) ADB has been repeatedly criticized for lack of international experience and professional standards of their TA recruited for the PLU (=inadequate) c) EC's experience is mixed. A long-term consultant was highly qualified in her field but found it difficult to adapt to the required role of monitoring, wanted to be closer involved in implementation, and left prematurely for a new assignment. Much better experience with targeted short- to medium-term consultancies (e.g. most recently on the MTBF for primary education) (=inadequate/adequate) | Quality is perceived by partner institution and Delegation as adequate. | Adequate (Del) | a) There has been no complaints about the LT TA. The LT TA has been successful in management and administration of the project although there are issues that are yet to be solved. b) There are mixed results. Some TAs are unable to provide proper recommendation to the GoB. Tariff Commission disagreed to appoint local TA through the int'l contract because of quality issues. c) Local TAs are working more in order to gain expertise and local capacity. |
| - TA Effectiveness | Only 1 is in place for long enough time to allow an assessment of this: Substitution has been effective and a prerequisite for the continuation of the sector programme; capacity building efforts have not resulted in measurable improvements | a) With increasing experience of GoB officials in managing the program, they also make better and more effective use of the TA available for them (=moderately effective). b) While the organizational setup of a separate PLU is considered effective for the monitoring of a sector program, the managing partner has been criticised for not getting best value for money in their TA recruitment (=moderately effective). c) The Delegation increasingly sees the use of TA for short, well-defined assignments more effective in supporting a sector program than the deployment of long-term experts (=moderately effective). | Moderately effective at strengthening government capacity. There is still resistance from the government to accept and comply with many issues included in the Peace Accord. Effective with regard to programme implementation. The recent ROM evaluation confirmed that. | Project is at a very early stage of implementation, hence TA effectiveness cannot yet be assessed | a) The performance of the projects depend not only on the TA but effectiveness can be seen only through a proper team work. My general opinion would be the TAs have been moderately effective in strengthening government capacity, and effective as regards implementation. |
| Comments | Main challenge is the absence of effective incentives, which would create an effective orientation to results in the public sector. | A general pattern emanating from discussions around TA among development partners is that the targeted recruitment of individual experts is seen as more effective than the tendering of "packages" through consultancy firms (always a "mixed bag"). For long-term capacity building, partners at local level are increasingly in favour of institutional partnerships and "twinnings" with Universities or research institutions, rather than traditional TA. | The main strength of UNDP must be seen in its mandate to operate in post-conflict situations. | Profound relevant knowledge and experiences | Recruitment through the FWC has been very difficult even more difficult as the local counterparts were contracted separate. For long-term capacity building "twinning" through the restricted tender was the most ineffective way of tendering. Breaking the tenders into very small amounts is also a negative issue as the good players around the market is not attracted. |

Box 2: How to fill up Table 1

| - Short Project/ Programme title | Please indicate which project/programme the TA position is linked to (e.g. health project, NAO support, education programme). If possible, please also indicate the accounting number to help us extract information from the CRIS and ROM systems for further reference. |
| --- | --- |
| - Financing modality | Please indicate which financing modality is being used : General Budget Support (GBS), Sector Budget Support (SBS), Pooled Funding (PF), Project (P) |
| - Description of the TAs component | Please briefly describe how the TA is structured, indicate how many long term TA positions there are, and where possible, how many of the positions are filled by international, local or regional TAs. |
| 4. Are the TAs part of or linked to a PIU? | Please indicate whether the long-term TA is part of a PIU, or closely linked to it (is the TA’s main function to support / work with a PIU?). For definitions see section F of the questionnaire. Please answer Yes or No. |
| 5 Type of role(s) played by the TAs | Please indicate the main role(s) played by the long-term TAs selecting up to three out of the following options: - Project/programme financial implementation (‘Controlling funds’) - please indicate if the TA performs the role of Imprest Accounting Officer - Programme/project technical implementation (including monitoring): please indicate if the TA performs the role of Imprest Administrator - Gap-filling in partner government institutions - Advisory work to partner government (mentoring, coaching, facilitating, etc) - Supporting internal reforms and domestic change processes - Training - Support to delegation - Project/programme identification and formulation - Other? (please specify) |
| 6 Centralised or decentralised management | Please indicate whether the TA component is managed centrally or by decentralised management. If the latter, please also specify the form of decentralised management used : Please answer by using the following letters: (A) decentralised management with ex ante controls (B) decentralised management with ex post controls, (C) direct decentralised management (D) public indirect decentralised management (E) private indirect decentralised management |
| 7 Level of partner government involvement | Please indicate how you would grade the level of involvement and leadership by the partner government in the design, selection and management of the long term TAs. Please answer: “low”, “medium”, or “high”. |
| 8 Who do the TAs report to in practice? | Please indicate who, in practice, the TAs report to on any major issues concerning their assignment. Please answer by using the following abbreviations: the Partner Government (PG) / the Delegation (Del)? |
| 9 TA quality | Please indicate whether the overall quality of the different TAs is considered to be: “adequate” or “inadequate”. Please add to this judgement whether these opinions originate from the partner institution (PI) and/ or the Delegation (Del). |
| 10 TA Effectiveness | Please give us your estimate of whether this TA is seen as overall “effective”, “moderately effective” or “ineffective”. Please add to this judgement whether you mean “effective at strengthening government capacity, in line with the aid effectiveness principles”, or “effective as regards project/ programme implementation and management”? |
| 11 Comments | Please provide us any other relevant comments on this TA, for instance on what you see as its main strengths and weaknesses. |

Part II: Exploring current practices and options for the future

This section aims at collecting your views and experience with TC, TA and PIUs. Experiences will vary from one case to the other depending on sector/area, therefore answer by referring to major trends. Add references to other cases/experiences particularly   relevant. Please report on "real life" practices.

A. Completing the picture: Technical cooperation in the EC’s assistance portfolio

1. What do you think is on average the proportion of technical cooperation in each EC project/ programmes in the country you work in? Please give a rough estimate.

a. Up to 20%

b. Up to 50%

c. Above 50%

d. Please comment if necessary

2. How would you judge the current overall supply of TA in your country, including long-term and short-term TA?

a. Oversupplied

b. Correctly supplied

c. Undersupplied

d. Please comment if necessary

And also underdemanded.

3. In the last three years have you had any significant experience of Twinning/peer support?

a. Yes

b. No

c. Please score the quality/effectiveness by H (high) / M (medium) / L (low) and provide basic information

4. In the last three years, have you had any significant experience with other forms of TC (see box 1 for definitions?)

a. Yes

b. No

c. Please score the quality/effectiveness by H (high) / M (medium) / L (low) and provide basic information where relevant

Low, for example training of a number of trade officials does not produce much impact as GoB rules prevent officials from staying more than 3 years in the same posting, experience is lost.

B.  TA design in project/programme formuation

5. Who in reality "wants" technical assistance?

a. Partner government

b. Delegation

c. HQ

d. Recommendation form the QSG process

e. Recommendations from evaluations/monitoring

f. Others – please specify

In the sectors programmes, the role of the donors’ community appears rather limited.

6. During identification and formulation of projects/programmes, is the role which TA may play in supporting development of local capacity  in the partner institution part of the discussion?

a. Yes

b. No

c. Please comment if necessary

7. During identification and formulation of projects/programmes, are the costs of technical assistance transparent enough for the Partner Government to explore an alternative use of resources (including other forms of technical cooperation)?

a. Yes

b. No

c. Please comment if necessary

8. Who, in practice, drafts the terms of reference of TAs?

a. Delegation

b. Government

c. Joint effort

d. Other consultants

e. Please comment if necessary

In the sectors programme, the donor group plays mainly this role

9. Does the QSG stimulate discussion on TA provision during programme preparation?

a. Yes

b. No

c. Please comment if necessary

10. Where do you see room for improvement in the design of TA interventions? Is there a need for more guidance, working tools or other support?

A tool should be created for providing an access to expertise from European research Institutions and other think-tanks which contribution appear essential for contribution to institutional building process and effective reform agenda. Also transfer of know-how should be ensured to Government and not only substituting Government.

C. Tendering and procurement of TA

11. Of the procedures stipulated in the Financial Regulations and the PRAG, which procedures do you use most for procuring technical assistance?

Call for tender/FWC

12. Please describe your experience of working with Framework Contracts:

a. To what extent do framework contracts allow you to get good quality TAs?

Unfortunately, FWCs in 20-30% of cases do not yield the required quality experts.

b. What are the TAs used for in practice?

i. Mainly working directly with the Partner Government

ii. Mainly supporting the work of the Delegations

c. What are your opinions on the cost effectiveness of Framework Contracts?

a. Positive

b. Negative

c. Other/ comment

13. What is your experience of using the international restricted tender procedure?

a. Satisfactory

b. Unsatisfactory

c. Other/comment  But too long, procedure should be shortened

14. Do you have any experience of using national (partner government) procurement procedures for procuring TA?

a. Yes

b. No

c. If yes, please tell us more

Issues around transparency, leakage of information, delays and quality.

15.  Are you aware of any other donors using country procedures to contract and manage TA? If yes, could you indicate who?

a. Yes

b. No

c. If yes, please tell us more

WB, ADB, notably with similar problems appearing under their supervision

16. Please give us your views on the use of local/regional TAs:

a. If possible, could you provide a rough estimate of the proportion of local/regional TAs actually used (despite the fact that EC procedures no longer make any distinction between these categories…) ?

Approx 50%

b. Do you have any views on the pros and cons of using local/regional consultants in your country?
A significant proportion of local consultants do not have the required capacities. Use of high proportion of local and regional consultants tends to favour recycling of existing knowledge and ideas and decreases innovative external views and inputs.

This practice constitutes a market incentive which in the medium term may prove impacting negatively on quality of programmes and results.

17. Do you see room for improvement concerning current practices on tendering and procuring TA?

a. Yes

b. No

c. If yes, please tell us where and how!

Procedures should be less time consuming and yield better quality. FWC procedure needs to be reviewed. Fees paid to experts should be guaranteed at a given level in order to get better quality. The fees practised compared favourably with other donors, but de facto the companies benefit from them and not the experts, as a final result we get a lower quality for similar disbursements.

D: Implementation of TA

18. Which of the roles played by TAs are seen by the delegations as most useful? Please tick the most relevant answers and indicate whether Partner Government (PG) view diverge significantly in the "comments" column

Table 2: Which TA roles are most appreciated?

|  | Most useful | Useful | Not useful | Neither | Comments |
| --- | --- | --- | --- | --- | --- |
| - Project/programme financial implementation (‘Controlling funds’) |  | X |  |  | PS may be less positive |
| - Project/programme technical implementation | X |  |  |  |  |
| - Gap-filling in partner government institutions | X |  |  |  |  |
| - Advisory work to partner government |  | X |  |  | PG disagrees |
| - Supporting internal reforms and domestic change processes | X |  |  |  | PG disagrees |
| - Training |  | X | X |  | High turn over of staff often limits usefulness |
| - Support to delegation |  | X |  |  |  |
| - Other? (please specify) |  |  |  |  |  |

19. Do the terms of reference of TAs adequately reflect the requirements of the position by the time they start their assignments? If not, are they amended in practice? YES

20. Following Question 8 in Table 1, if relevant, please comment on the reporting and accountability relations of TAs: Who, in practice, do they feel accountable to? Delegation and PG

21. How is TA performance monitored in practice and by whom? Does monitoring lead to changes in the assignment? Please tick the relevant answer below and provide further comments if you wish.

Table 3: Who monitors TA?

|  | Yes / No | Comments |
| --- | --- | --- |
| The partner government |  |  |
| The partner government and the Delegation | Yes |  |
| The Delegation |  |  |
| ROM missions | Yes |  |
| Not at all |  |  |

E. Evaluation

22. What are the lessons learned, for TC/TA, from the evaluations of projects and programmes? Do you see a need to evaluate TC/TA components separately?

No need for separate evaluation of TA if TOR for project evaluations are sufficiently relevant and precise.

F. Questions on PIUs

Box 4: Current OECD - DAC definition of PIUs

For the purpose of this exercise, we use DAC definitions on PIU as follows. A project implementation unit (PIU) is a dedicated management unit designed to support the implementation and administration of projects or programmes. PIUs can be 'parallel’ or ‘integrated’, as defined below:

Parallel PIU:

A PIU is parallel when it is created outside existing country institutional structures. PIUs are said to be parallel when they meet at least three of the four criteria set out below:

- Q1: Is the PIU accountable to the external funding agencies or donor rather than to the country implementing agencies (ministries, departments, agencies etc)? (YES/NO)

- Q2: Are the terms of reference for externally appointed staff determined by the donor (rather than by the country implementing agencies)? (YES/NO)

- Q3: Is most of the professional staff appointed by the donor rather than the country implementing agencies? (YES/NO)

- Q4: Is the salary structure of staff higher than those of civil service personnel. (YES/NO)

Integrated PIU:

  - If there are fewer than 3 ‘yes’ answers, than the PIU qualifies as integrated.

NB: In practice, the format and features of PIU will vary according to the country context. In some cases, PIUs are fully national structures with TAs supporting them. In others, TAs are integrated within the PIU. Please apply DAC definitions to your country context and indicate if there are major divergences

23. Could you give a rough estimate of the proportion of projects which use PIUs in the country you work in?

NA

24. Please fill in the table below for at least the "5 top programmes" implemented through a PIU in your country (including support units to NAO for EDF) and answer the questions referring to  the above definitions

Table 5: Mapping the main PIUs

| PIU linked to project/ programme name | Q1: PIU accountable to? | Q2: TOR of external staff drafted by? | Q3: Most professional PIU staff appointed by? | Q4: Is the salary structure higher than that of the civil service? | Position and role of TA* |
| --- | --- | --- | --- | --- | --- |
| PEDP-II (5813) | Government | Government, supervised by lead donor | Government, supervised by lead donor | Yes | Yes and No PEDP-II Program Coordination Unit (PCU): integrated in government structures. Responsibilities: 1, 2, 3, 4, 5, 6; no Imprest responsibility. |
| BTSP | Government | Delegation and the PTF | Government | Yes | 1, 2, 3, 4, 5, 6; no Imprest responsibility. |
| CHTDF | Del and GoB | EC/UNDP | UNDP | Yes | Not integrated |
| VGDUP | PG | Delegation | Delegation | For TA yes, for local staff no | Yes integrated, Training and supporting PG in project mgt |
| HNPSP | Government | Donor group/Gvt | Lead donor | Yes | Yes and No1,2,3,4,5,6 |

* Please indicate whether the TA is formally integrated in the PIU (YES / NO). If YES: please specify, what the main roles of the TA are (refer to the roles described in section 5, Box 2)

25. What, in your opinion, should be done to increase domestic ownership and quality of project implementation set ups and to meet the EU aid effectiveness target ("avoid the establishment of any new PIUs")?

Increase collaboration with civil society and private sector. Only work with those PG institutions which have the necessary capacity and will to deliver. Avoid working with those PG institutions which are inefficient, ineffective, indifferent and incompetent
Reinforce Gvt capacity.

26. Please comment on the Paris target n. 6 of reducing the stock of existing PIUs by 2/3rds by 2010:

a. Given your current portfolio, do you expect that this target can be met? YES

b. What should be done and by whom (Delegation, HQ, PG, TA, etc….) to facilitate this process? PG should commit itself to public finance reform for putting in place the conditions for SWAP or budget support.

c. Are there any national or donor initiatives to reach this target?

Indirectly yes, through adequate programmes but not as an ad hoc initiative.

27. For EDF countries: In your view, is there a prospect of phasing out "parallel PIUs" supporting  NAOs offices by 2010?

28. Do you have any other comments on PIUs?

G. Role played by the partner government

29. Is there any national policy or strategic guidance on TC/TA, or an effort to coordinate TC/TA interventions by the partner government, in the country you work in? Please give details.

a. Yes

b. No

c. Please comment if necessary

30. Further to the information you gave in Table 1 – question 7, do you have any additional comments on the level of overall partner government involvement/ownership on technical assistance and on how to promote it:

|  | Comments on PG involvement |
| --- | --- |
| TA Design | Limited |
| TA Procurement | There should be a results oriented approach for creating a need, otherwise high temptation to go for national TA without much result. Exchange of experience, expertise for pushing reform agenda appears necessary. |
| TA Management |  |

H. Donor coordination on TC/TA and PIUs

31. Please comment on donor coordination in the country you work in:

a. Is there any process in place to increase coordination focusing on TC and PIU issues in line with the Paris Declaration and the EU aid effectiveness targets?

a. Yes

b. No

c. If yes, what has been the outcome of these processes so far? For example within HNPSP. Difficult to assess at this stage.

d. Please comment if necessary

b. Are there any pool funds for technical cooperation? Are you participating in them?

a. Yes

b. No

c. Please comment

32. Please comment on the EU target of coordinating "100% of capacity building assistance" by 2010:

a. Given your current portfolio, do you expect that this target can be met? YES

b. What should be done and by whom (Delegation, HQ, PG, other donors TA, etc….) to facilitate this process/ to work more through joint approaches?

c. Are there any national or donor initiatives to reach this target?

I. Looking forward and collecting your ideas on the future strategy

33. Please analyse in the table below future needs of TC by sector/area of work.

Table 6: Future needs for Long-term TAs in your country

| Main sector/ working areas | Need of future TAs (H, M, L), | Role of TAs* | Other forms of TC** | Comments |
| --- | --- | --- | --- | --- |
| Health | H | Advisory and gap filling | Twinning, Peer support, research |  |
| Education | H | Same |  |  |
| Agriculture | H | Advisory | research |  |

* Please use types specified in Question 5, Box 2.

** Other forms of TC: Please use “types” specified in Box 1.

How would you judged the overall trend for future needs of TA against current practices?

a) steady

b) decreasing

c) increasing

34. Are you aware of any TA financed through the national budget? Would budget support be an option to support fully nationally owned TA integrated in the partner government’s budget?No but not completely sure, maybe in education some TA is financed under national budget

35. Your views on how best to support capacity development process led by partner governments ? what are the pro and cons of TA in this respect?

36. What in your view, are the major issues/areas of change that the future strategy on technical cooperation and PIUs should deal with? Please indicate the 3 most important from the list below and tell us why !!!

a. Develop a clear policy and guidance material

b. Support/promote coordination with member states/other donors

c. Support country/ sector dialogue with Partner Government

d. Rules/ financial regulations

e. Review contracting procedures developed by EuropeAid (Practical Guide, Programme Estimate, etc)

f. Consider issues related to management and capacity/expertise in delegation

g. Update methodology and develop ad hoc tools (PCM/SWAP,QSG systems/ROM, TOR..)

h. Training/ workshops/ seminars

i. Information/ communication

j. Other (please specify) …………

37. Are there any major good or bad stories you would like to tell us, including suggestions for cases we should look at more deeply (if yes, please provides references and background documentation)?

Additional comments? Please use this space for any insights or thoughts you wish to share

Annexe 1 to the questionnaire

Proposed areas for change and for actions

This matrix shows in the column a preliminary list of axes of the future strategy/workplan.  Delegations views are particularly important in the sections shown in red.

| Areas of change/actions | Design and formulation |  | TA/TC procurement | Implementation Monitoring |  | Evaluation |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Content and format of EC policy and guidance on TC and PIU |  |  |  |  |  |  |  |
| How to foster coordination with member states and other donors |  |  |  |  |  |  |  |
| How to foster Country/ sector dialogue with Partner Government |  |  |  |  |  |  |  |
| Focus on Financial Management EC Rules (Focus on the FR) |  |  |  |  |  |  |  |
| Review of the Financial and Contracting procedures developed by EuropeAid (PRAG, Programme Estimates Guide, etc…) |  |  |  |  |  |  |  |
| Review of methodology, guidance, QSG systems (checklists, etc…), monitoring and ROM |  |  |  |  |  |  |  |
| Training |  |  |  |  |  |  |  |
| Information/ communication |  |  |  |  |  |  |  |
| Management issues and capacity/expertise at delegation level (including incentives, workload and tasks) |  |  |  |  |  |  |  |
| Any other areas resulting from this survey |  |  |  |  |  |  |  |

Key documents are posted on the AIDCO intranet, see the menu “Revisiting Technical Cooperation and PIUs" : :http://www.cc.cec/dgintranet/europeaid/activities/adm/technical_cooperation/index_en.htm and on the D_Groups site

For a definition of PIUs please see section F of this questionnaire.

It's up to the delegation to select the programmes where the TA component is particularly significant and relevant for this survey (innovative approach, good and bad practices,  importance of the financial envelope, etc)

There are many different definitions of capacity. The Aid Delivery Methods Concept Paper Institutional Assessment an Capacity Development – Why? what and how? (September 2005) defines it as follows (p.5): “Capacity is the ability to perform tasks and produce outputs, to define and solve problems, and make informed choices.”

These questions address PIUs linked to programmes supporting classical public sector functions

It's up to the delegation to select these programme,  as the most significant for this survey (including  in terms of diversity of practices and arrangements).

For instance on what type of TA will be sought for what purposes.

Including BS – SWAP and new sectors/areas of intervention (migration, climate change ….),